## Final
PROJECTS |  |  |  | Possible Add'l Work
| Project | Description | Status | Notes for 2017 | Possible Project?
FUNDED PRIOR TO FALL 2016 | T-intersection test(s) (short radius) |  |  | Still want to fund a "phase 2"? | YES
| MASH Testing of Free-Standing and Pinned Temporary Concrete Barrier | Oregon pin-and-loop barrier evaluated to MASH TL-3 criteria in free-standing configuration. Barrier also tested with pins angled into concrete deck to bring restrained barrier system fully up to MASH criteria. | Free-standing barrier succesfully tested with full-amtrix. Test of barrier restrained to concrete deck failed. Recommend re-testing with offset from edge of deck. | Retest barrier restrained to concrete deck with offset from deck edge. Critical test is MASH 3-11. Full matrix would also require MASH 3-10. Sticking with "due diligence" approach, right? This will be discussed with all other portable barriers during the scorecard 3b discussion. | YES
Missing any?
Results of Last Year's Voting
[6 empty] | DOT1 | DOT2 | DOT3 | DOT4 | DOT5 | DOT6 | DOT7 | DOT8 | DOT9 | DOT10 | DOT11 | DOT12 | DOT13 | DOT14 | DOT15 | DOT16 | DOT17 | Tot | TL-2 / TL-3 / TL-4 / TL-5 | Preliminary Test Conduction Cost ($) | Preliminary System Construction Cost ($) | Preliminary Cost ($) (rough estimates, subject to change) | Total ($) | DOT Representative
FUNDED at FALL 2016 MEETING | TL-4 on 42" barrier - CIP Foundation Study | Objective; to determine the minimum foundation requirements for a 42” tall barrier for TL-4 conditions. | This project did not start, as Texas funded a similiar project. 42" SSCB succesfully tested with 1"-asphalt key. Length was 75'. The budgeted funds will be added back into the "account". | Does this satisfy project objective? Can run additional MASH Test 4-12 with shorter segment length using existing test installation. Currently,any segment length <75' will require dowels accross joint. | YES | [21 empty] | 82000 | 82000 | D. Sheppard (FL)
| Scorecard 3 support | Information gathering and organizing for the multiple scorecards that will be used at the annual meeting | Ongoing | See "Other", below for details potential tasks to discuss with team | NO | [21 empty] | 80000 | 162000 | J. Petterson (WA)
| 1:1 slope test(s) (Additional phase of prior project) | Conduct full-scale crash testing MGS with 8" block-outs placed on a 1H:1V slope. Guardrail face aligned with the break point of the slope. Tests MASH 3-10 and MASH 3-11 will be conducted. | Crash tests planned for November 2017 . | No future phases/work anticipated (on Scorecard 1, also) | NO | 8 | 6 | 7 | 4 | 5 | 9 | 9 | 5 | 5 | 10 | 9 | 6 | 8 | 6 | 10 | N/A | 9 | 116 | TL-3 | 77400 | 20000 | 97400 | 259400 | D. Hardy/J. Hall (WV)
| 31" W-Beam Guardrail w/ steel (and wood) posts in concrete mow strip | Test MGS w/ 8" block-outs in concrete mow strip. Both steel and wood post options will be tested to MASH Test Level 3 criteria. | Testing of steel post system on-going. MASH Test 3-10 succesful. Test 3-11 scheduled for October. Wood post testing scheduled for November 2017 | No future phases/work anticipated (on Scorecard 1, also) | NO | 0 | 8 | 9 | 6 | 9 | 3 | 5 | 10 | 10 | 7 | 7 | 10 | 10 | 4 | 8 | N/A | 10 | 116 | TL-3 | 154800 | 36000 | 190800 | 450200 | M. Elle (MN)
| T-intersection test(s) (short radius) | Full-scale crash test recommendations made from Phase I of this project, which involves analysis of design application variations for short radius system. | This project did not start, as Phase 1 is still being worked on. Will be discussed under "ongoing projects, next steps" The budgeted funds will be added back into the "account". | See "Funded Prior to 2016" section | NO | 7 | 10 | 1 | 10 | 4 | 10 | 1 | 6 | 7 | 4 | 8 | 5 | 1 | 9 | 6 | N/A | 8 | 97 | TL-3 | 77400 | 20000 | 97400 | 547600 | C. Lindsey (TX)
| MGS-Compatible Buried in Backslope | The purposes of this research are to full-scale crash test and evaluate the performance of a 31-inch Buried-In-Backslope (BIB) terminal design compatible with an MGS guardrail system. | Testing Planned for November 2017 | SEE SCORECARD 2 | NO | 9 | 7 | 8 | 9 | 10 | 6 | 7 | 0 | 0 | 9 | 10 | 0 | 6 | 7 | 7 | N/A | 1 | 96 | TL-3 | 77400 | 30000 | 107400 | 655000 | J. Jefferson (AK)
| Raised Blocks Crash Test | The purposes of this research are to full-scale crash test and evaluate the performance of a W-beam rail system with 8-inch blockouts raised on steel posts as a mean for adjusting rail height. | DD Approach completed. | SEE SCORECARD 1 | NO | 0 | 9 | 10 | 8 | 8 | 4 | 10 | 7 | 4 | 5 | 2 | 1 | 7 | 2 | 4 | N/A | 4 | 85 | TL-3 | 41000 | 11620 | 52620 | 707620 | A. Hangul (TN)
2016 UNFUNDED (DIDN'T MAKE THE CUT) | MGS w/ 12ft 6in post spacing (curb) to MASH TL-2 | Test MGS system (8" blockouts) at 12' 6" post spacing (with curb) to MASH TL-2. Prior test without curb succesful. NOTE: there is a planned MwRSF test for MGSat 6'3" post spacing on curb and omitted post (or on curb only) at TL-3 |  | SEE SCORECARD 1 |  | 1 | 5 | 5 | 1 | 7 | 2 | 4 | 8 | 0 | 0 | 4 | 9 | 9 | 10 | 0 | N/A | 6 | 71 | TL-2
| MGS w/ flare | Test MGS system (8" blockouts) at different flare rates. Which flare rates should be tested? |  | SEE SCORECARD 1 |  | 5 | 3 | 4 | 2 | 1 | 8 | 6 | 0 | 6 | 3 | 0 | 8 | 5 | 8 | 0 | N/A | 0 | 59 | TL-3
| 31" Stacked W-Beam Transition (continuation of prior pooled fund work) | Modify and re-evalaute stacked W-beam transition for 31" guardrail. Under pooled fund project 604581, the stacked W-beam transition did not perform succesfully for MASH Test 3-21 due to rollover event. |  | SEE SCORECARD 3a |  | 3 | 0 | 3 | 5 | 0 | 5 | 8 | 0 | 8 | 0 | 3 | 0 | 3 | 1 | 9 | N/A | 7 | 55 | TL-3
| MGS down from 8:1 slope break | Test MGS system (8" blockouts) down 8:1 slope break. |  | SEE SCORECARD 1 |  | 6 | 4 | 6 | 0 | 0 | 7 | 3 | 9 | 1 | 6 | 1 | 2 | 2 | 3 | 0 | N/A | 0 | 50 | TL-3
| MGS Non-Blocked - with reduced post spacing | Test MGS system with no blockouts, and reduced post spacing. |  | Didn't make the cut last year, want to add it back on? | YES | 0 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 2 | 8 | 6 | 7 | 0 | 0 | 0 | N/A | 3 | 31 | TL-3
| MGS Non-Blocked (double sided median) | Test double sided median version of MGS, no blockouts, and reduced post spacing. |  | Didn't make the cut last year, want to add it back on? | YES | 4 | 1 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 1 | 5 | 3 | 0 | 0 | 5 | N/A | 2 | 26 | TL-3
| PennDOT Weak Post System | Test PennDOT weak post system MASH 3-10. NOTE: Test succesfully conducted at TTI for PennDOT. Now have full matrix for this sytem. |  | SEE SCORECARD 1 |  | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | N/A | 0 | 7 | TL-3
POSSIBLE OTHER TASKS | Scorecard preparation for 2018 meeting | Finish 3e Bridge railS. Do we want a 3f (sign supports, breakaway hardware)? Do we want a 4 (temporary work zone)? |  |  | YES
| Scorecards as the team’s implementation status tracking tool | Do we want to make the investment to circle back to the scorecards we have used so far (scorecard 1 through scorecard 3d), and add any of your state’s systems (that are not already on the scorecard), to track MASH compliance for systems? Example: if you have a cast-in-place barrier not currently shown on the scorecards, we could add it, and investigate the MASH compliancy status and report the result on the scorecard. An advantage to this approach is that the systems you use then become part of the national discussion regarding MASH implementation, as they are tracked, and we can speak to those systems or categories that will not meet the implementation schedule. |  |  | YES
| Professional opinion/“Due diligence” documentation support | Support for documentation of MASH compliance for different systems following the “due diligence” approach. Give examples of what this could be: |  |  | YES
| Bridge rail support (other than scorecard development) | Is there anything that can be done (synopsis? What is the NCHRP panel doing? Anything?) that would position us better for next year’s discussions on bridge rail? |  |  | YES