## Sheet1
Caltrans Projects - Bridge Rails |  |  | Caltrans Projects - Breakaway |  |  | Caltrans Projects - Breakaway
Projects | Tests Planned/ Conducted | Tests Deemed Not Critical | Projects | Tests Planned/ Conducted | Tests Deemed Not Critical | Projects | Tests Planned/ Conducted | Tests Deemed Not Critical
Type 732SW TL-2 Bridge Rail | 2-10 3-11 |  | Type 15 - FBS (18 ft. tall breakaway Flashing Beacon Pole System) | Testing has commenced but is a lower priority |  | Two post sign support | Project not started yet
ST-70SM TL-4 Side Mount Barrier | 4-10 4-11 4-12
Type 60 Median Barrier | 3-10
Type 836 | not tested, crashworthiness evaluated based on other testing and structural load analysis
Type 842 | not tested, crashworthiness evaluated based on other testing and structural load analysis
Type 85 Concrete Bridge Rail | TL-4 (Expected 2018)
ST-75 | TL-4 (Expected 2019)
State Historic Concrete Bridge Rail - Post and Beam | in concept phase