## Table of Contents
Monthly Reports for WSDOT Pooled Fund Projects
Reporting Month: |  |  |  | 2023-07-01
Project Number | Task Order | SME State Rep. | Prinicipal Investigator | Project Title | Link to Report
609971 | T4541-CV | Tim Moeckel (WA) | Roger Bligh | Testing & Evaluation of the MGS System with the Maximum Flare at MASH TL3 Conditions | Link to Report
615251 | T4541-DY | Tim Moeckel (WA) | Akram Abu-Odeh | MASH TL-3 Transition Design with a Storm Drain Inlet | Link to Report
616011 | T4541-EC | Dean Kanitz (MI) | Nathan Schulz | Development and Evaluation of a Non-Proprietary Sign Support System for MASH Test Level 3 Conditions | Link to Report
616001 | T4541-ED | Mary McRae (AK) | Roger Bligh | Guidelines for Attaching MASH-Compliant Thrie-Beam Transitions to Rigid Concrete Barriers other than the Rigid Barrier Tested | Link to Report
616161 | T4541-EI | D. Sheppard (FL) | Nauman Sheikh | Crashworthy Enhanced Highway Sign Assemblies | Link to Report
616401 | T4541-EM | Ted Whitmore (WV) | James Kovar | Multi-Directional Breakaway Devices | Link to Report
616811 | T4541-EN | Bob Meline (CA) | Nauman Sheikh | Development of a MASH TL-3 Compliant Portable Concrete Barrier System | Link to Report
617231 | T4541-EP | Tim Moeckel (WA) | Nauman Sheikh | Evaluation of Long-Span W-Beam Guardrail in Front of Fall-Protection Rail on Concrete Culverts | Link to Report
617721 | T4541-EQ | Tim Moeckel (WA) | Nauman Sheikh | 2022 Program Development and MASH Coordination Effort | Link to Report
617731 | T4541-ER | Jim Danila (MA) | William Williams | Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States | Link to Report
617741 | T4541-ES | Derwood Sheppard (FL) | Nauman Sheikh | MASH 4-12 Evaluation of a Fence Mounted System for Attachments to Concrete Bridge Barrier | Link to Report
617771 | T4541-ET | Ted Whitmore (WV) | Akram Abu-Odeh | MASH Testing of a Guardrail System on 1H:1V Slope | Link to Report
617781 | T4541-EU | Andy Pott (CO) | William Williams | Funding for Strain Gauge Deck and Barrier Optimization for Roadside Safety Issues/Problems for Member States | Link to Report
617891 | T4541-EV | Derwood Sheppard (FL) | Sofokli Cakalli | MASH Crashworthy Pedestrian and Small Traffic Signals | Link to Report
617881 | T4541-EW | Tim Moeckel (WA) | Nauman Sheikh | 2022 Administrative Support | Link to Report
617871 | T4541-EX | Mary McRae (AK) | Sofokli Cakalli | Buried-in-Backslope Terminal Variations in Foreslope, Backslope, and Ditch Configurations | Link to Report
618141 | T4541-EY | Tim Moeckel (WA) | William Williams | Washington State I-90 Snoqualmie Pass Barrier Gap Full-Scale Crash Testing | Link to Report
618851 | T4541-FB | Evan Pursel (PA) | Nathan Schulz | MASH TL-3 Evaluation of a Median Guide Rail Transition to Median F-Shape Concrete Barrier | Link to Report
618911 | T4541-FC | Shawn Debehnam (UT) | James Kovar | Evaluation of a Four Bolt Slip Base for Breakaway Luminaire Supports with Various Pole Configurations | Link to Report
618901 | T4541-FD | Brian Crossley (PA) | James Kovar | Portable Sign Supports for Aluminum Signs with Variations on Mounting Height | Link to Report
618981 | T4541-FE | Ted Whitmore (WV) | William Williams | MASH Test Level 3 Evaluation of a Shorter Thrie-Beam Approach Transition | Link to Report
619441 | T4541-FF | Chris Lindsey (TX) | Nauman Sheikh | Steel-Post W-Beam Guardrail in Asphalt Mow-Strip | Link to Report
619651 | T4541-FG | Alex Lim (OR) | Nathan Schulz | Evaluation of Open Joints in Concrete Bridge Rail Systems | Link to Report
619591 | T1969-AA | Tim Moeckel (WA) | Nauman Sheikh | 2023 Program Development & Coordination Effort | Link to Report
619621 | T1969-AB | Tim Moeckel (WA) | James Kovar | Optimized Guardrail Blockouts | Link to Report
619611 | T1969-AC | Erik Emerson (WI) | Nauman Sheikh | W-Beam Guradrail in Front of Retaining Wall or Rip Rap | Link to Report
619631 | T1969-AD | Tim Moeckel (WA) | James Kovar | Barrier Deflections at Lower Impact Severities | Link to Report
619601 | T1969-AE | Carlos Torres (MI) | William Williams | Phase 2 Thrie Beam Retrofit - Application of New Design without a Curb for MASH TL-3 and Performance and Improvements for MASH TL-4 | Link to Report
619541 | T1969-AF | Flint Jackson (WA) | Nathan Schulz | MASH TL-3 Evaluation of Sign Posts with Flashing Beacon Equipment | Link to Report
619551 | T1969-AG | Derwood Sheppard (FL) | Akram Abu-Odeh | MASH TL-3 Transition Design with a Storm Drain Inlet, Phase II | Link to Report

## 609971
TPF No. | 5(343)
Project No. | 609971
Task Order No. | CV
Supplementary | No
Project Title | Testing & Evaluation of the MGS System with the Maximum Flare at MASH TL3 Conditions
Month/Year | 2023-07-01
PI Name | Roger Bligh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
The final report for this project has been approved and submitted. The project is in close out.
Comments / Issues
None.

## 615251
TPF No. | 5(343)
Project No. | 615251
Task Order No. | DY
Supplementary | No
Project Title | MASH TL-3 Transition Design with a Storm Drain Inlet
Month/Year | 2023-07-01
PI Name | Akram Abu-Odeh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
Draft report is completed, and it is being reviewed before submission to the state technical representative.
Comments / Issues
None.

## 616011
TPF No. | 5(343)
Project No. | 616011
Task Order No. | EC
Supplementary | No
Project Title | Development and Evaluation of a Non-Proprietary Sign Support System for MASH Test Level 3 Conditions
Month/Year | 2023-07-01
PI Name | Nathan Schulz
SME State Rep. Name | Dean Knatiz (MI)
Work Completed This Month
Project is complete. Final invoice submitted.
Comments / Issues
None.

## 616001
TPF No. | 5(343)
Project No. | 616001
Task Order No. | ED
Supplementary | No
Project Title | Guidelines for Attaching MASH Thrie-Beam Transitions to Rigid Concrete Barriers other than the Rigid Barrier Tested
Month/Year | 2023-07-01
PI Name | Roger Bligh
SME State Rep. Name | Mary McRae (AK)
Work Completed This Month
The draft final report is in preparation. Guidance has been developed for attachment of thrie beam transitions to other parapets than the one tested. The guidance is based on previous testing and a limited simulation effort. The guidance includes use of different barrier profiles with specified taper below the thrie beam depending on the profile shape. The guidance also addresses height transition rate when attaching the transition to a taller parapet than the one tested. The use of a parapet wall extension when attaching the transition to a tall wall such as a retaining wall, tunnel, sound wall, etc., is also addressed. The draft report should be completed and transmitted to the technical representative for review near the end of the next reporting month.
Comments / Issues
None.

## 616161
TPF No. | 5(343)
Project No. | 616161
Task Order No. | EI
Supplementary | Yes
Project Title | Crashworthy Enhanced Highway Sign Assemblies
Month/Year | 2023-07-01
PI Name | Nauman Sheikh (Previously Maysam Kiani)
SME State Rep. Name | Derwood Sheppard (FL)
Work Completed This Month
This project has been completed and the final report was submitted and approved by the Tech. Rep. No further work was performed in the reporting preiod.
Comments / Issues
None.

## 616401
TPF No. | 5(343)
Project No. | 616401
Task Order No. | EM
Supplementary | No
Project Title | Multi-Directional Breakaway Devices
Month/Year | 2023-07-01
PI Name | James Kovar
SME State Rep. Name | Ted Whitmore (WV)
Work Completed This Month
The research team has been modifying the current fuse plate design to improve activation during an impact. In the previous crash test, the delay in fuse plate activation caused the sign panel to drop and impact the vehicle. Therefore, the fuse plate was redesigned. The research team sent the revised drawings to the technical representative for review and approval. The technical representative approved the drawings.
Comments / Issues
None.

## 616811
TPF No. | 5(343)
Project No. | 616811
Task Order No. | EN
Supplementary | Yes
Project Title | Development of a MASH TL-3 Compliant Portable Concrete Barrier System
Month/Year | 2023-07-01
PI Name | Nauman Sheikh
SME State Rep. Name | Bob Meline (CA)
Work Completed This Month
Discussed various options for testing of the PCB segments on concrete with reduced anchor embedement. Prepared and submitted for review drawings of the test installation for the PCB system anchored on concrete with reduced embedment. Answered several other inquiries from Caltrans related to implementation of the PCB systems, including use of longer segment lenghts, segment weights, etc. Prepared samples of connections loops to send to Caltrans for material testing. On approval of the drawings, the researchers started working on construction of the test installation.
Comments / Issues
None.

## 617231
TPF No. | 5(343)
Project No. | 617231
Task Order No. | EP
Supplementary | Yes
Project Title | Evaluation of Long-Span W-Beam Guardrail in Front of Fall-Protection Rail on Concrete Culverts
Month/Year | 2023-07-01
PI Name | Nauman Sheikh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
This project was completed on June 30, 2023. The final report has been submitted. No further work was performed in the reporting period.
Comments / Issues
None.

## 617721
TPF No. | 5(343)
Project No. | 617721
Task Order No. | EQ
Supplementary | No
Project Title | 2022 Program Development and MASH Coordination Effort
Month/Year | 2023-07-01
PI Name | Nauman Sheikh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
Various administrative support tasks were performed in this month to support the Pooled Fund program. These included preparing for the preliminary meetings and general reporting and accounting tasks.
Comments / Issues
None.

## 617731
TPF No. | 5(343)
Project No. | 617731
Task Order No. | ER
Supplementary | No
Project Title | Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States
Month/Year | 2023-07-01
PI Name | Nauman Sheikh (Previously William Williams)
SME State Rep. Name | Jim Danialla (MA)
Work Completed This Month
TTI has recevied new funding to start work on some of the new requests for professional engineering opinions. TTI team has started discussion on which of the recevied opinion requests can be completed in the funds available, and which researchers could be assigned those tasks. TTI will provide a more detailed update the selected professional opinions in the next couple of weeks.
Comments / Issues
None. Nauman is the PI for this project.

## 617741
TPF No. | 5(343)
Project No. | 617741
Task Order No. | ES
Supplementary | No
Project Title | MASH 4-12 Evaluation of a Fence Mounted System for Attachments to Concrete Bridge Barrier
Month/Year | 2023-07-01
PI Name | Nauman Sheikh (Previously Maysam Kiani)
SME State Rep. Name | Derwood Sheppard (FL)
Work Completed This Month
The research team completed evaluation of the new design under MASH Test 4-21 conditions using simulation analysis. The results were shared with the Tech. Rep. about the proposed design for crash testing. The design that is likely to pass Test 4-21 based on simulation is comprised of posts that are laterally offset from the barrier. A longitudinal pipe was also added to the top of the posts. The combination of the offset posts and the longitudinal posts helped keep the fence posts from interacting with the cab of the truck, mitigating the mode of failure in the past testing. Tech. Rep. desired to have the fence attached to the offset posts. TTI research team worked on the concept that achieved keeping the fence attaced to the posts and it was approved by the Tech. Rep. TTI team then started working of developing the full test installation drawings of the barrier and fence system.
Comments / Issues
None.

## 617771
TPF No. | 5(343)
Project No. | 617771
Task Order No. | ET
Supplementary | No
Project Title | MASH Testing of a Guardrail System on 1H:1V Slope
Month/Year | 2023-07-01
PI Name | Akram Abu-Odeh
SME State Rep. Name | Ted Whitmore (WV)
Work Completed This Month
Draft report is completed, and it is being reviewed before submission to the state technical representative.
Comments / Issues
None.

## 617781
TPF No. | 5(343)
Project No. | 617781
Task Order No. | EU
Supplementary | No
Project Title | Funding for Strain Gauge Deck and Barrier Optimization for Roadside Safety Issues/Problems for Member States
Month/Year | 2023-07-01
PI Name | William Williams
SME State Rep. Name | Andy Pott (CO)
Work Completed This Month
All strain gage data from the recent crash test on the TXDOT luminiaire pole atop the SSTR was sent to the sponsor on 6/23/23. No additional instrumentation work was performed in July. We are awaiting the next project to use instrumentation.
Comments / Issues
None.

## 617891
TPF No. | 5(343)
Project No. | 617891
Task Order No. | EV
Supplementary | No
Project Title | MASH Crashworthy Pedestrian and Small Traffic Signals
Month/Year | 2023-07-01
PI Name | Sofokli Cakalli
SME State Rep. Name | Derwood Sheppard (FL)
Work Completed This Month
In the month of July, the researchers gathered the survey answers and prepared a summary of results. After presenting the results to the technical representatives, a decision was made to move foraward with the testing of Option B, which consists of a pedestrian signal height mounted on a 4-inch OD pipe with a clearance of 10 ft. This represents the mounting height limit reccomended by MUTCD. Installation details were developed for the selected configuration. The Proving Ground is currently working to obtain the parts. Also, the MASH TL-3 crash tests are now scheduled for September 5 and 6. A no cost time extension for the project was requested and approved until December 31, 2023.
Comments / Issues
A no-cost time extension for this project was requested and apporved until 12/31/2023 .

## 617881
TPF No. | 5(343)
Project No. | 617881
Task Order No. | EW
Supplementary | No
Project Title | 2022 Administrative Support
Month/Year | 2023-07-01
PI Name | Nauman Sheikh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
Various administrative support tasks were performed in this month to support the Pooled Fund program. These included preparing for meetings and general reporting and accounting tasks.
Comments / Issues
None.

## 617871
TPF No. | 5(343)
Project No. | 617871
Task Order No. | EX
Supplementary | No
Project Title | Buried-in-Backslope Terminal Variations in Foreslope, Backslope, and Ditch Configurations
Month/Year | 2023-07-01
PI Name | Sofokli Cakalli
SME State Rep. Name | Mary McRae (AK)
Work Completed This Month
The FE model of the modified guardrail system for the MASH compliant BIB terminal was completed. Preliminary validation simulations were conducted. The model validation and verification process will continue in the month of July. If adequate progress is made, variations in the terrrain will be instegated.
Comments / Issues
A no-cost time extension until 12/31/2023 was requested and approved for this project.

## 618141
TPF No. | 5(343)
Project No. | 618141
Task Order No. | EY
Supplementary | No
Project Title | Washington State I-90 Snoqualmie Pass Barrier Gap Full-Scale Crash Testing
Month/Year | 2023-07-01
PI Name | William Williams
SME State Rep. Name | Tim Moeckel
Work Completed This Month
TTI still has noot received the barrier shipment at the end of this reporting period (July 2023). We tentatively have the crash test scheduled for 8/21. At this time of this writing (8/4) we have received all the barrier units and they look ready for testing!
Comments / Issues
None.

## 618851
TPF No. | 5(343)
Project No. | 618851
Task Order No. | FB
Supplementary | No
Project Title | MASH TL-3 Evaluation of a Median Guide Rail Transition to Median F-Shape Concrete Barrier
Month/Year | 2023-07-01
PI Name | Nathan Schulz
SME State Rep. Name | Evan Pursel (PA)
Work Completed This Month
Detailed drawings of system developed. Meeting held with tech reps to discuss drawings.
Comments / Issues
None.

## 618911
TPF No. | 5(343)
Project No. | 618911
Task Order No. | FC
Supplementary | No
Project Title | Evaluation of a Four Bolt Slip Base for Breakaway Luminaire Supports with Various Pole Configurations
Month/Year | 2023-07-01
PI Name | James Kovar
SME State Rep. Name | Shawn Debenham (UT)
Work Completed This Month
The research team has been investigating the effects of weight, C.G., and height have on the trajectory of luminaire poles during an impact. The research team has reviewed previous luminaire tests to gain insight in crashworthy systems. The research team has drafted a testing plan and begun preparing drawings. The research team will send the technical representative the drawings and test plan in August for review and approval.
Comments / Issues
None.

## 618901
TPF No. | 5(343)
Project No. | 618901
Task Order No. | FD
Supplementary | No
Project Title | Portable Sign Supports for Aluminum Signs with Variations on Mounting Height
Month/Year | 2023-07-01
PI Name | James Kovar
SME State Rep. Name | Brian Crossley
Work Completed This Month
The research team has drafted the test plan and installation drawings based upon discussions with the technical representatives. The plan and drawings will be sent to the technical representatives for review and approval in August.
Comments / Issues
None.

## 618981
TPF No. | 5(343)
Project No. | 618981
Task Order No. | FE
Supplementary | No
Project Title | MASH Test Level 3 Evaluation of a Shorter Thrie-Beam Approach Transition
Month/Year | 2023-07-01
PI Name | William Williams (Previously Maysam Kiani)
SME State Rep. Name | Ted Whitmore (WV)
Work Completed This Month
TTI resent drawings to the sponsor for construction this reporting period (from May 17, 2023) . The sponsor approved the design and we are proceeding with construction. We plan to pour the concrete parapet for the transition early next reporting period.
Comments / Issues
None.

## 619441
TPF No. | 5(343)
Project No. | 619441
Task Order No. | FF
Supplementary | No
Project Title | Steel-Post W-Beam Guardrail in Asphalt Mow-Strip
Month/Year | 2023-07-01
PI Name | Nauman Sheikh
SME State Rep. Name | Chris Lindsey (TX)
Work Completed This Month
TTI team perfomed a series of bogie tests comprising of eight tests. In these tests, the posts were installed in asphalt at different offsets from the edge of the 2-inch thick and 3-inch thick asphalt pads. The offset distances ranged from 6 inches to 12 inches. Two of the eight tests were performed on posts embeded in soil. The goal of these tests was to determine a post in asphalt configuration that matches the force-deflection response of the posts directly installed in soil. The researchers performed the testing over two separate days. The results of the tests comprised of accelaration-time histories measured from the impacting bogie vehicle. The histroies were processed by the research team to determine the force-defleciton response of the posts. The researchers compared the results of these tests to guide the various configurations that were tested. The researchers started the process of determining the configuration that is expected to perform similar to post embedded directly in soil. This configuration will be recommeded for full-scale crash testing of the W-beam guardrail installed in asphalt mow-strip.
Comments / Issues
None.

## 619651
TPF No. | 5(343)
Project No. | 619651
Task Order No. | FG
Supplementary | No
Project Title | Evaluation of Open Joints in Concrete Bridge Rail Systems
Month/Year | 2023-07-01
PI Name | Nathan Schulz
SME State Rep. Name | Alex Lim (OR)
Work Completed This Month
Completed review of previous crash testing of concrete bridge rails with open joints.
Comments / Issues
None.

## 619591
TPF No. | 5(501)
Project No. | 619591
Task Order No. | FG
Supplementary | No
Project Title | 2023 Program Development & Coordination Effort
Month/Year | 2023-07-01
PI Name | Nauman Sheikh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
Various administrative support tasks were performed in this month to support the Pooled Fund program. These included preparing for meetings and general reporting and accounting tasks.
Comments / Issues
None.

## 619621
TPF No. | 5(501)
Project No. | 619621
Task Order No. | AB
Supplementary | No
Project Title | Optimized Guardrail Blockouts
Month/Year | 2023-07-01
PI Name | James Kovar
SME State Rep. Name | Tim Moeckel
Work Completed This Month
The research team has been investigating previously failed w-beam crash tests for causation. The objective of this investigation is to find failed crash tests which can be attributed to rail and blockout interaction. Once these tests are identified, a new shape/size of blockout could be developed. The research team is planning to meet with the technical representative this month to review the current status of this investigation.
Comments / Issues
None.

## 619611
TPF No. | 5(501)
Project No. | 619611
Task Order No. | AC
Supplementary | No
Project Title | W-Beam Guardrail in Front of Retaining Wall or Rip Rap
Month/Year | 2023-07-01
PI Name | Nauman Sheikh
SME State Rep. Name | Erik Emerson
Work Completed This Month
The research team reviewed different options of the concrete retaining wall and the steel pile sheet retaining wall with Tech Rep for use in the project. This task is still ongoing. The researchers also reviewed several past tests to select a representative test of the MGS system for use in the project. This past test will be used for validation of the W-beam guardrail simulation model and for film analysis to determine suitable for Rip Rap.
Comments / Issues
None.

## 619631
TPF No. | 5(501)
Project No. | 619631
Task Order No. | AD
Supplementary | No
Project Title | Barrier Deflections at Lower Impact Severities
Month/Year | 2023-07-01
PI Name | James Kovar
SME State Rep. Name | Tim Moeckel
Work Completed This Month
The research team sent a survey to state DOTs requesting priorities for evaluating barrier systems for impacts with lower severities. The survey was closed in late July, and the research team compiled the responses. The top three priorities are MGS with full-post spacing, F-shape concrete barrier (unanchored), and F-shape concrete barrier (anchored). The research team is planning to meet with the technical representative to discuss the simulation effort plan.
Comments / Issues
None.

## 619601
TPF No. | 5(501)
Project No. | 619601
Task Order No. | AE
Supplementary | No
Project Title | Phase 2 Thrie Beam Retrofit: Applying New Design w/o Curb for MASH TL-3 & Performance & Improvements for TL-4
Month/Year | 2023-07-01
PI Name | William Williams
SME State Rep. Name | Carlos Torres (MI) & Derwood Sheppard (FL)
Work Completed This Month
A project kickoff meeting was held on May 25,2-23. TTI is continuing to work on simulating the current "as-tested" thrie beam design with a curb for MASH TL-4. The research team has converted the "AS-Tested" Solidworks model into the LS-DYNA Mesh this reporting period.
Comments / Issues
None.

## 619541
TPF No. | 5(501)
Project No. | 619541
Task Order No. | AF
Supplementary | No
Project Title | MASH TL-3 Evaluation of Sign Posts with Flashing Beacon Equipment
Month/Year | 2023-07-01
PI Name | Nathan Schulz
SME State Rep. Name | Flint Jackson (WA)
Work Completed This Month
Completed review of previous crash testing with breakaway support structures and equipment assemblies.
Comments / Issues
None.

## 619551
TPF No. | 5(501)
Project No. | 619551
Task Order No. | AG
Supplementary | No
Project Title | MASH TL-3 Transition Design with a Storm Drain Inlet, Phase II
Month/Year | 2023-07-01
PI Name | Akram Abu-Odeh
SME State Rep. Name | Derwood Sheppard
Work Completed This Month
Crash test data and report materials being assmebled and drafted for the draft final report.
Comments / Issues
None.