## Table of Contents
Monthly Reports for WSDOT Pooled Fund Projects
Reporting Month: |  |  |  | 2023-08-01
Project Number | Task Order | SME State Rep. | Prinicipal Investigator | Project Title | Link to Report
615251 | T4541-DY | Tim Moeckel (WA) | Akram Abu-Odeh | MASH TL-3 Transition Design with a Storm Drain Inlet | Link to Report
616001 | T4541-ED | Mary McRae (AK) | Roger Bligh | Guidelines for Attaching MASH-Compliant Thrie-Beam Transitions to Rigid Concrete Barriers other than the Rigid Barrier Tested | Link to Report
616161 | T4541-EI | D. Sheppard (FL) | Nauman Sheikh | Crashworthy Enhanced Highway Sign Assemblies | Link to Report
616401 | T4541-EM | Ted Whitmore (WV) | James Kovar | Multi-Directional Breakaway Devices | Link to Report
616811 | T4541-EN | Bob Meline (CA) | Nauman Sheikh | Development of a MASH TL-3 Compliant Portable Concrete Barrier System | Link to Report
617231 | T4541-EP | Tim Moeckel (WA) | Nauman Sheikh | Evaluation of Long-Span W-Beam Guardrail in Front of Fall-Protection Rail on Concrete Culverts | Link to Report
617721 | T4541-EQ | Tim Moeckel (WA) | Nauman Sheikh | 2022 Program Development and MASH Coordination Effort | Link to Report
617731 | T4541-ER | Jim Danila (MA) | Nauman Sheikh | Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States | Link to Report
617741 | T4541-ES | Derwood Sheppard (FL) | Nauman Sheikh | MASH 4-12 Evaluation of a Fence Mounted System for Attachments to Concrete Bridge Barrier | Link to Report
617771 | T4541-ET | Ted Whitmore (WV) | Akram Abu-Odeh | MASH Testing of a Guardrail System on 1H:1V Slope | Link to Report
617781 | T4541-EU | Andy Pott (CO) | William Williams | Funding for Strain Gauge Deck and Barrier Optimization for Roadside Safety Issues/Problems for Member States | Link to Report
617891 | T4541-EV | Derwood Sheppard (FL) | Sofokli Cakalli | MASH Crashworthy Pedestrian and Small Traffic Signals | Link to Report
617881 | T4541-EW | Tim Moeckel (WA) | Nauman Sheikh | 2022 Administrative Support | Link to Report
617871 | T4541-EX | Mary McRae (AK) | Sofokli Cakalli | Buried-in-Backslope Terminal Variations in Foreslope, Backslope, and Ditch Configurations | Link to Report
618141 | T4541-EY | Tim Moeckel (WA) | William Williams | Washington State I-90 Snoqualmie Pass Barrier Gap Full-Scale Crash Testing | Link to Report
618851 | T4541-FB | Evan Pursel (PA) | Nathan Schulz | MASH TL-3 Evaluation of a Median Guide Rail Transition to Median F-Shape Concrete Barrier | Link to Report
618911 | T4541-FC | Shawn Debehnam (UT) | James Kovar | Evaluation of a Four Bolt Slip Base for Breakaway Luminaire Supports with Various Pole Configurations | Link to Report
618901 | T4541-FD | Brian Crossley (PA) | James Kovar | Portable Sign Supports for Aluminum Signs with Variations on Mounting Height | Link to Report
618981 | T4541-FE | Ted Whitmore (WV) | William Williams | MASH Test Level 3 Evaluation of a Shorter Thrie-Beam Approach Transition | Link to Report
619441 | T4541-FF | Chris Lindsey (TX) | Nauman Sheikh | Steel-Post W-Beam Guardrail in Asphalt Mow-Strip | Link to Report
619651 | T4541-FG | Alex Lim (OR) | Nathan Schulz | Evaluation of Open Joints in Concrete Bridge Rail Systems | Link to Report
619591 | T1969-AA | Tim Moeckel (WA) | Nauman Sheikh | 2023 Program Development & Coordination Effort | Link to Report
619621 | T1969-AB | Tim Moeckel (WA) | James Kovar | Optimized Guardrail Blockouts | Link to Report
619611 | T1969-AC | Erik Emerson (WI) | Nauman Sheikh | W-Beam Guradrail in Front of Retaining Wall or Rip Rap | Link to Report
619631 | T1969-AD | Tim Moeckel (WA) | James Kovar | Barrier Deflections at Lower Impact Severities | Link to Report
619601 | T1969-AE | Carlos Torres (MI) | William Williams | Phase 2 Thrie Beam Retrofit - Application of New Design without a Curb for MASH TL-3 and Performance and Improvements for MASH TL-4 | Link to Report
619541 | T1969-AF | Flint Jackson (WA) | Nathan Schulz | MASH TL-3 Evaluation of Sign Posts with Flashing Beacon Equipment | Link to Report
619551 | T1969-AG | Derwood Sheppard (FL) | Akram Abu-Odeh | MASH TL-3 Transition Design with a Storm Drain Inlet, Phase II | Link to Report
620061 | T1969-AI | David Kilpatrick (CT) | Nathan Schulz | Design and MASH Full-Scale Crash Testing and Evaluation of the Merritt Parkway Guiderail | Link to Report
619991 | T1969-AH | Mustafa Mohamedali (WA) | Roger Bligh | 2023 Travel and Meeting Assistance | Link to Report

## 619991
TPF No. | 5(501)
Project No. | 619991
Task Order No. | AH
Supplementary | No
Project Title | 2023 Travel and Meeting Assistance
Month/Year | 2023-08-01
PI Name | Roger Bligh
SME State Rep. Name | Mustafa Mohamedali
Work Completed This Month
A poll was sent out to members to determine the number of expected meeting attendees and associated room nights needed. The hotel contract was signed and room block secured. The travel letter and related materials were sent to the state members. The meeting facility was reserved. Catered lunches during the meeting were planned. Planning for the group dinner was initiated.
Comments / Issues

## 615251
TPF No. | 5(343)
Project No. | 615251
Task Order No. | DY
Supplementary | No
Project Title | MASH TL-3 Transition Design with a Storm Drain Inlet
Month/Year | 2023-08-01
PI Name | Akram Abu-Odeh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
Work continued on editing the draft final report. Planning for report submittal to the technical rep by the end of September.
Comments / Issues

## 616001
TPF No. | 5(343)
Project No. | 616001
Task Order No. | ED
Supplementary | No
Project Title | Guidelines for Attaching MASH Thrie-Beam Transitions to Rigid Concrete Barriers other than the Rigid Barrier Tested
Month/Year | 2023-08-01
PI Name | Roger Bligh
SME State Rep. Name | Mary McRae (AK)
Work Completed This Month
The draft final report is still in preparation. The draft final report and its associated guidance for attaching crash tested transitions to parapets other than the one tested will be completed and transmittted to the technical representative during the next reporting month. My sincere apologies for the further delay in completing this effort.
Comments / Issues

## 616161
TPF No. | 5(343)
Project No. | 616161
Task Order No. | EI
Supplementary | Yes
Project Title | Crashworthy Enhanced Highway Sign Assemblies
Month/Year | 2023-08-01
PI Name | Nauman Sheikh (Previously Maysam Kiani)
SME State Rep. Name | Derwood Sheppard (FL)
Work Completed This Month
This project has been completed and the final report was submitted and approved by the Tech. Rep. No further work was performed in the reporting preiod.
Comments / Issues

## 616401
TPF No. | 5(343)
Project No. | 616401
Task Order No. | EM
Supplementary | No
Project Title | Multi-Directional Breakaway Devices
Month/Year | 2023-08-01
PI Name | James Kovar
SME State Rep. Name | Ted Whitmore (WV)
Work Completed This Month
The research team received approval from the technical representative for design changes which are to be evaluated through MASH crash testing. The updated designs were sent for fabrication, and the parts are scheduled for delivery in early September. The research team will proceed with MASH crash testing as soon as possible.
Comments / Issues

## 616811
TPF No. | 5(343)
Project No. | 616811
Task Order No. | EN
Supplementary | Yes
Project Title | Development of a MASH TL-3 Compliant Portable Concrete Barrier System
Month/Year | 2023-08-01
PI Name | Nauman Sheikh
SME State Rep. Name | Bob Meline (CA)
Work Completed This Month
TTI is constructing the test installation for the fourth MASH Test 3-11 with reduced embedment epoxy anchors. The test installation is expected to me ready in September. The crash test has been scheduled for September 15, 2023.
Comments / Issues

## 617231
TPF No. | 5(343)
Project No. | 617231
Task Order No. | EP
Supplementary | Yes
Project Title | Evaluation of Long-Span W-Beam Guardrail in Front of Fall-Protection Rail on Concrete Culverts
Month/Year | 2023-08-01
PI Name | Nauman Sheikh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
This project was completed on June 30, 2023. The final report has been submitted. No further work was performed in the reporting period.
Comments / Issues

## 617721
TPF No. | 5(343)
Project No. | 617721
Task Order No. | EQ
Supplementary | No
Project Title | 2022 Program Development and MASH Coordination Effort
Month/Year | 2023-08-01
PI Name | Nauman Sheikh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
Various administrative support tasks were performed in this month to support the Pooled Fund program. These included preparing for the preliminary meetings and general reporting and accounting tasks.
Comments / Issues

## 617731
TPF No. | 5(343)
Project No. | 617731
Task Order No. | ER
Supplementary | No
Project Title | Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States
Month/Year | 2023-08-01
PI Name | Nauman Sheikh (Previously William Williams)
SME State Rep. Name | Jim Danialla (MA)
Work Completed This Month
TTI has started work on two engineering opinions requests that are listed below: - WSDOT low-profile barrier MASH compliance based on testing of TxDOT Low-Profile Barrier and Florida Low-Profile Barrier. - Evaluation of reduced anchor pin length for the anchored PCB on asphalt.
Comments / Issues
Currently, the project only has approximately $9,000 left for 2023. There are 3 to 4 additional requests for engineering opinions that need to await execution of the FY2023 task order for this project before the work can begin. TTI will be contacting WSDOT to request execution of the FY2023 Task Order.

## 617741
TPF No. | 5(343)
Project No. | 617741
Task Order No. | ES
Supplementary | No
Project Title | MASH 4-12 Evaluation of a Fence Mounted System for Attachments to Concrete Bridge Barrier
Month/Year | 2023-08-01
PI Name | Nauman Sheikh (Previously Maysam Kiani)
SME State Rep. Name | Derwood Sheppard (FL)
Work Completed This Month
TTI developed the drawings for the test installation and obtained approval of the Technical Representative for full-scale crash testing. TTI then started construction of the test installation.
Comments / Issues

## 617771
TPF No. | 5(343)
Project No. | 617771
Task Order No. | ET
Supplementary | No
Project Title | MASH Testing of a Guardrail System on 1H:1V Slope
Month/Year | 2023-08-01
PI Name | Akram Abu-Odeh
SME State Rep. Name | Ted Whitmore (WV)
Work Completed This Month
Work continued on editing the draft final report. Planning for report submittal to the technical rep by the end of September.
Comments / Issues

## 617781
TPF No. | 5(343)
Project No. | 617781
Task Order No. | EU
Supplementary | No
Project Title | Funding for Strain Gauge Deck and Barrier Optimization for Roadside Safety Issues/Problems for Member States
Month/Year | 2023-08-01
PI Name | William Williams
SME State Rep. Name | Andy Pott (CO)
Work Completed This Month
No work was performed this reporting period.
Comments / Issues

## 617891
TPF No. | 5(343)
Project No. | 617891
Task Order No. | EV
Supplementary | No
Project Title | MASH Crashworthy Pedestrian and Small Traffic Signals
Month/Year | 2023-08-01
PI Name | Sofokli Cakalli
SME State Rep. Name | Derwood Sheppard (FL)
Work Completed This Month
The pedestrian signal with 10-ft ground clearance was crash tested under MASH 3-62 conditions, which consistst of a pickup truck at an impact speed of 100 mph and angle of 90 deg. The configuration did not pass MASH 3-62 test. This configuration was selected by the pooled fund members based on the current MUTCD guidelines. The researchers will analyze the test results and coordinate with the technical representative to discuss the path forward.
Comments / Issues

## 617881
TPF No. | 5(343)
Project No. | 617881
Task Order No. | EW
Supplementary | No
Project Title | 2022 Administrative Support
Month/Year | 2023-08-01
PI Name | Nauman Sheikh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
Various administrative support tasks were performed in this month to support the Pooled Fund program. These included preparing for meetings and general reporting and accounting tasks.
Comments / Issues

## 617871
TPF No. | 5(343)
Project No. | 617871
Task Order No. | EX
Supplementary | No
Project Title | Buried-in-Backslope Terminal Variations in Foreslope, Backslope, and Ditch Configurations
Month/Year | 2023-08-01
PI Name | Sofokli Cakalli
SME State Rep. Name | Mary McRae (AK)
Work Completed This Month
The researchers made several modifications to improve the quality of the FE model. Simulations were run with gravity and prescribed forces to test the system before conducting full scale validation simulations. The simulations showed that the system was stable. A full scale validation simulation was initiated and is currently underway.
Comments / Issues

## 618141
TPF No. | 5(343)
Project No. | 618141
Task Order No. | EY
Supplementary | No
Project Title | Washington State I-90 Snoqualmie Pass Barrier Gap Full-Scale Crash Testing
Month/Year | 2023-08-01
PI Name | William Williams
SME State Rep. Name | Tim Moeckel
Work Completed This Month
MASH Crash Test 3-10 was performed on the Shoqualmie Pass Barrier Gap Barrier. The crash test was successful!
Comments / Issues
It was learned after the crash test that the barriers were constructed incorrectly (wrong longitudinal rebar). New barriers are currently being constructed.

## 618851
TPF No. | 5(343)
Project No. | 618851
Task Order No. | FB
Supplementary | No
Project Title | MASH TL-3 Evaluation of a Median Guide Rail Transition to Median F-Shape Concrete Barrier
Month/Year | 2023-08-01
PI Name | Nathan Schulz
SME State Rep. Name | Evan Pursel (PA)
Work Completed This Month
Construction is in progress. Deck reinforcement was layed out and concrete was poured for the deck.
Comments / Issues

## 620061
TPF No. | 5(501)
Project No. | 620061
Task Order No. | AI
Supplementary | No
Project Title | Design and MASH Full-Scale Crash Testing and Evaluation of the Merritt Parkway Guiderail
Month/Year | 2023-08-01
PI Name | Nathan Schulz
SME State Rep. Name | David Kilpatrick (CT)
Work Completed This Month
Comments / Issues
Project begins Sep. 1. No work completed for August.

## 618911
TPF No. | 5(343)
Project No. | 618911
Task Order No. | FC
Supplementary | No
Project Title | Evaluation of a Four Bolt Slip Base for Breakaway Luminaire Supports with Various Pole Configurations
Month/Year | 2023-08-01
PI Name | James Kovar
SME State Rep. Name | Shawn Debenham (UT)
Work Completed This Month
The research team modeled a variety of pole configurations which states submitted to the survey. The weights and CG's of these pole configurations were analyzed with respect to similar ongoing research regarding luminaire poles. The research team began developing the final testing plan and will submit it to the technical representative for review and approval in early September.
Comments / Issues

## 618901
TPF No. | 5(343)
Project No. | 618901
Task Order No. | FD
Supplementary | No
Project Title | Portable Sign Supports for Aluminum Signs with Variations on Mounting Height
Month/Year | 2023-08-01
PI Name | James Kovar
SME State Rep. Name | Brian Crossley
Work Completed This Month
The research team developed details of two portable sign support systems in pursuit of state needs. Both systems were discussed with the technical representative panel, and the taller stand was approved for testing. The research team began analyzing the shorter stand with respect to a variety of sign shapes and sizes. The research team will submit drawings of the recommended shorter sign stand for review and approval in early September.
Comments / Issues
None.

## 618981
TPF No. | 5(343)
Project No. | 618981
Task Order No. | FE
Supplementary | No
Project Title | MASH Test Level 3 Evaluation of a Shorter Thrie-Beam Approach Transition
Month/Year | 2023-08-01
PI Name | William Williams (Previously Maysam Kiani)
SME State Rep. Name | Ted Whitmore (WV)
Work Completed This Month
The current test installation is currently being constructed for MASH Test 3-21 next reporting period.
Comments / Issues

## 619441
TPF No. | 5(343)
Project No. | 619441
Task Order No. | FF
Supplementary | No
Project Title | Steel-Post W-Beam Guardrail in Asphalt Mow-Strip
Month/Year | 2023-08-01
PI Name | Nauman Sheikh
SME State Rep. Name | Chris Lindsey (TX)
Work Completed This Month
TTI made recommendations for full-scale crash testing based on bogie test results. The recommendation was presented to and approved by the Technical Represtative. TTI also developed installation drawings of the test article for full-scale crash testing. On approval of the test installations by the Technical Representative, TTI started construction of the test installation.
Comments / Issues

## 619651
TPF No. | 5(343)
Project No. | 619651
Task Order No. | FG
Supplementary | No
Project Title | Evaluation of Open Joints in Concrete Bridge Rail Systems
Month/Year | 2023-08-01
PI Name | Nathan Schulz
SME State Rep. Name | Alex Lim (OR)
Work Completed This Month
Began developing survey questions to distribute to PF state members to collect additional information on their standard details for open joints.
Comments / Issues

## 619591
TPF No. | 5(501)
Project No. | 619591
Task Order No. | FG
Supplementary | No
Project Title | 2023 Program Development & Coordination Effort
Month/Year | 2023-08-01
PI Name | Nauman Sheikh
SME State Rep. Name | Tim Moeckel
Work Completed This Month
Various administrative support tasks were performed in this month to support the Pooled Fund program. These included preparing for meetings and general reporting and accounting tasks.
Comments / Issues

## 619621
TPF No. | 5(501)
Project No. | 619621
Task Order No. | AB
Supplementary | No
Project Title | Optimized Guardrail Blockouts
Month/Year | 2023-08-01
PI Name | James Kovar
SME State Rep. Name | Tim Moeckel
Work Completed This Month
The research team reviewed previous failed MASH crash tests of guardrail systems for the behavior of the wood blockouts. The research team also investigated other shapes and sizes of blockouts which could be suitable for MGS installations. Lastly, the research team met with the technical representative to provide a status update.
Comments / Issues

## 619611
TPF No. | 5(501)
Project No. | 619611
Task Order No. | AC
Supplementary | No
Project Title | W-Beam Guardrail in Front of Retaining Wall or Rip Rap
Month/Year | 2023-08-01
PI Name | Nauman Sheikh
SME State Rep. Name | Erik Emerson
Work Completed This Month
TTI researchers had a meeting with the Tech. Rep. to discuss some recommeded changes on how simulation can be used in the project for yielding information that will have broader applicability. Previous research approach involved using a specific concrete retaining wall or a steel sheet pile design, which would have led the results of the simulation to be restricted to the specific wall design. The researchers proposed performing the guardrail impact simulations without a specific retaining wall and detemining the lateral load from a vehicle impact at various offsets from the guardrail. Using this information, a more generalized guidance can be provided when designing a retaining wall. The guidance is expected to provide lateral load that should be incorporated in retaining wall design due to the presence of a guardrail at a certain offset from the wall. This approach was accepted by the Technical Representative. TTI continued developing the model of the W-beam gaurdrail system for the dynamic impact simulations.
Comments / Issues

## 619631
TPF No. | 5(501)
Project No. | 619631
Task Order No. | AD
Supplementary | No
Project Title | Barrier Deflections at Lower Impact Severities
Month/Year | 2023-08-01
PI Name | James Kovar
SME State Rep. Name | Tim Moeckel
Work Completed This Month
The research team collected responses to the state survey, in which states were asked to prioritize their needs for deflection information from impacts at lower severities. A portable f-shape concrete barrier system and an MGS were both prioritized for evaluation through computer simulation. Models were developed for each of the systems, and validation efforts for these models were started. The research team also met with the technical representative to discuss the results of the survey.
Comments / Issues

## 619601
TPF No. | 5(501)
Project No. | 619601
Task Order No. | AE
Supplementary | No
Project Title | Phase 2 Thrie Beam Retrofit: Applying New Design w/o Curb for MASH TL-3 & Performance & Improvements for TL-4
Month/Year | 2023-08-01
PI Name | William Williams
SME State Rep. Name | Carlos Torres (MI) & Derwood Sheppard (FL)
Work Completed This Month
The research team has developed a finite element mesh of the deck and curb reinforcement and concrete. Appropriate section and material properties have been applied to these parts. The research team is also preparing engineering analyses on the new design usinng Mathcad 8.0 Prime (new software).
Comments / Issues

## 619541
TPF No. | 5(501)
Project No. | 619541
Task Order No. | AF
Supplementary | No
Project Title | MASH TL-3 Evaluation of Sign Posts with Flashing Beacon Equipment
Month/Year | 2023-08-01
PI Name | Nathan Schulz
SME State Rep. Name | Flint Jackson (WA)
Work Completed This Month
Categorized information collected from literature review. Began developing survey questions to distribute to PF state members to collect additional information equpiment attached to sign posts.
Comments / Issues

## 619551
TPF No. | 5(501)
Project No. | 619551
Task Order No. | AG
Supplementary | No
Project Title | MASH TL-3 Transition Design with a Storm Drain Inlet, Phase II
Month/Year | 2023-08-01
PI Name | Akram Abu-Odeh
SME State Rep. Name | Derwood Sheppard
Work Completed This Month
Testing was successful. Draft final report was developed and being reviewed. Planning for report submittal to the technical rep by the end of September.
Comments / Issues