## 5-343 MASH (Phase 2)
TPF-5(343) MASH Pooled Fund: |  | Committed vs Obligated Status |  | v.230123 | Obligation status updated per Mara 1/23 |  |  | commitment amount in $1,000's |  |  |  |  | y = | obligated | n = | not obligated | [7 empty] | March 25, 2022 Snapshot
[24 empty] | Committed in 2022 and 2023 committed to TPF 5(343) | Obligated in 2022 and committed for 2023 to TPF 5(343) | Committed in 2022 | Obligated in 2022 | No 2022 commitment but otherwise ok | No 2022 commitment and issue in at least one more year | Phase 3 intention
ID# | Organization | Technical Contact Name | Funding Contact Name | Contact Number | Email Address | Flag | Tot/State | 2016 | Obl | 2017 | Obl | 2018 | Obl | 2019 | Obl | 2020 | Obl | 2021 | Obl | 2022 | Obl | 2023 | Obl | [6 empty] | 650000
1 | Alabama Department of Transportation | Stan Biddick | Virgil Clifton | 334-353-6944 | cliftonv@dot.state.al.us |  | 250 |  |  |  |  | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | [5 empty] | y
2 | Alaska Department of Transportation and Public Facilities | Mary McRae | Anna Bosin | (907)269-6208 | anna.bosin@alaska.gov | X | 150 | 25 | y | 25 | y | 25 | y | 25 | y | 25 | y | 25 | y | 25 | y |  |  |  |  | y
3 | California Department of Transportation | John Jewell | Sang Le | (916)701-3998 | sang.le@dot.ca.gov |  | 300 |  |  | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 |  |  | y |  |  |  |  | y
4 | Colorado Department of Transportation | Josh Keith | David Reeves | 303-757-9518 | david.reeves@state.co.us |  | 250 |  |  |  |  | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 |  |  | y |  |  |  |  | y
5 | Connecticut Department of Transportation | David Kilpatrick | Melanie Zimyeski | (860)594-2144 | Melanie.Zimyeski@ct.gov |  | 150 | 10 | y | 10 | y | 10 | y | 10 | y | 10 | y | 50 | y | 50 | y | [5 empty] | y
6 | Delaware Department of Transportation | Anne Brown | Anne Brown | (302) 760-2198 | anne.brown@state.de.us | X | 75 | [6 empty] | 25 | y | 50 | y | 25 | y | 50 | y | [7 empty] | y
7 | Florida Department of Transportation | Derwood Sheppard | Jennifer Clark | 850-414-4614 | jennifer.clark@dot.state.fl.us | X | 300 | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 |  | y | [5 empty] | y
8 | Idaho Department of Transportation | Marc Danley | Ned Parrish | 208-334-8296 | ned.parrish@itd.idaho.gov |  | 200 | 8.8 | y | 25 | y | 16.2 | y | 25 | y | 25 | y | 50 | y | 50 | y |  |  |  |  | y
10 | Illinois Department of Transportation | Filiberto Sotelo | Megan Swanson | 217-782-3547 | Megan.Swanson@illinois.gov |  | 300 | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y |  | ? | [6 empty] | y
9 | Iowa Department of Transportation | Daniel Harness | Cheryl Cowie | 515-239-1447 | Cheryl.Cowie@iowadot.us |  | 200 | [6 empty] | 50 | y | 50 | y | 50 | y | 50 | y | 50 |  |  | y |  |  |  |  | y
11 | Louisiana Department of Transportation and Development | Kurt Brauner | Tyson Rupnow |  | tyson.rupnow@la.gov | X | 300 | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | n | 50 |  | y | [5 empty] | y
12 | Maryland Department of Transportation State Highway Administration | Matamba Kabengele | Sharon Hawkins | 410-545-2920 | shawkins2@mdot.maryland.gov | X | 75 | [6 empty] | 25 | y | 25 | y | 25 | y | 25 | y |  |  |  |  | y
13 | Massachusetts Department of Transportation | Neil Boudreau | Lily Oliver | (857)368-9025 | hongyan.oliver@state.ma.us |  | 300 |  |  | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 |  | y | [5 empty] | y
14 | Michigan Department of Transportation | Carlos Torres | Andre' Clover | 517-749-9001 | clovera@michigan.gov | X | 250 |  |  | 50 | y | 50 | y |  |  | 100 | y | 50 | y | 50 | y | 50 |  | y | [5 empty] | y
15 | Minnesota Department of Transportation | Michael Elle | Debbie Sinclair | 651-336-3746 | debbie.sinclair@state.mn.us | X | 300 | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | [6 empty] | y |  | y
16 | Mississippi Department of Transportation | Heath Patterson | Robert Vance |  | RVance@mdot.ms.gov |  | 100 | [6 empty] | 50 | y | 50 | y | [11 empty] | y
17 | Missouri Department of Transportation | Ronald Effland | Jennifer Harper | 573-526-3636 | Jennifer.Harper@modot.mo.gov |  | 250 |  |  |  |  | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | [5 empty] | y
18 | New Mexico Department of Transportation | [5 empty] | 200 | [6 empty] | 50 | y | 50 | y | 50 | y | 50 | y | [7 empty] | y
19 | Ohio Department of Transportation | Don Fisher | General Research | 614-644-8135 | Research@dot.state.oh.us |  | 200 | [6 empty] | 50 | y | 50 | y | 50 | y | 50 | y | 50 |  | y | [5 empty] | y
20 | Oklahoma Transportation | Hebret Bokhru | Ron Curb | (405)420-9163 | rcurb@odot.org |  | 30 |  |  | 10 | y | 10 | y | 10 | y
21 | Ontario Ministry of Transportation | [5 empty] | 200 |  |  |  |  | 50 | y | 50 | y | 50 | y |  |  | 50 | y | [6 empty] | y
22 | Oregon Department of Transportation | Heidi Shoblom | Michael Bufalino | 503-986-2845 | Michael.Bufalino@odot.state.or.us |  | 300 | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | [8 empty] | y
23 | Pennsylvania Department of Transportation | TBD | Heather Sorce | 717-214-9508 | hsorce@pa.gov | X | 300 | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y |  |  |  |  | y
24 | Tennessee Department of Transportation | Ali Hangul | Melanie Murphy | 615-253-2158 | melanie.murphy@tn.gov |  | 300 |  |  | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | [5 empty] | y
25 | Texas Department of Transportation | Christopher Lindsey | Ned Mattila | 512-416-4727 | ned.mattila@txdot.gov | X | 300 | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | n |  |  |  |  | y
26 | Utah Department of Transportation | Shawn Debenham | David Stevens | 801-589-8340 | davidstevens@utah.gov |  | 175 |  |  |  |  | 25 | y | 25 | y | 25 | y | 50 | y | 50 | y |  |  |  |  | y
27 | Washington State Department of Transportation | John Donahue | Mustafa Mohamedali | 360-704-6307 | MOHAMEM@wsdot.wa.gov |  | 160 | 10 | y | 25 | y | 25 | y | 25 | y | 25 | y | 25 | y | 25 | y
28 | West Virginia Department of Transportation | Donna Hardy | Perry Keller | (304)558-9591 | Perry.J.Keller@wv.gov |  | 125 |  |  | 25 | y | 25 | y | 25 | y | 25 | y | 25 | y | [9 empty] | y
29 | Wisconsin Department of Transportation | [5 empty] | 300 |  |  | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y | 50 | y |  |  |  |  | y |  |  |  | y
[24 empty] | 5 | 3 | 7 | 4 | 4 | 4 | 10
| FFY Totals >>> | [5 empty] | Totals 2016-2022 | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023
| Total # of states committed | [6 empty] | 11 |  | 18 |  | 23 |  | 28 |  | 28 |  | 26 |  | 24 |  | 8
| Total # of states obligated | [6 empty] | 11 |  | 18 |  | 23 |  | 28 |  | 28 |  | 26 |  | 22 |  | 0
| Total # of states if filter active | [6 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 26 |  | 1 |  | 0
| Total committed | [5 empty] | 6765 | 403.8 |  | 720 |  | 936.2 |  | 1145 |  | 1260 |  | 1175 |  | 1125 |  | 400
| Total obligated | [5 empty] | 6665 | 403.8 |  | 720 |  | 936.2 |  | 1145 |  | 1260 |  | 1175 |  | 1025 |  | 0
| Total arrears | [5 empty] | 100 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 100 |  | 400
| Totals if filter active | [5 empty] | 1325 | 8.8 |  | 25 |  | 16.2 |  | 25 |  | 25 |  | 1175 |  | 50 |  | 0
Note on G3: Mohamedali, Mustafa: User flag to custom filter
Note on W3: Mohamedali, Mustafa: 2023 figures not included in calculations or summaries. See Phase 3 tab
Note on C5: Mohamedali, Mustafa: See email 7/11/22 Mary McRae
Note on V5: Mohamedali, Mustafa: Per Mara email 8/23
Note on S6: Mohamedali, Mustafa: Total transfer was $500k which included $50k per commitment plus $450k for supplementary studies.
Note on U7: Mohamedali, Mustafa: $90k obligated which includes $40k for a supplementary study
Note on T9: Mohamedali, Mustafa: see Blowers email 4/27/22 fwd by Donahue 4/27/22 4/10/23 update: DelDOT transferred $25k out of the blue!
Note on V9: Mohamedali, Mustafa: see Blowers email 4/27 fwd by Donahue 4/27
Note on V10: Mohamedali, Mustafa: per Mara email 8/23
Note on I11: Mohamedali, Mustafa: Not sure if this total obligated
Note on M11: Mohamedali, Mustafa: Not sure if this is total obligated
Note on V11: Mohamedali, Mustafa: Per Mara email 4/11
Note on X13: Mohamedali, Mustafa: A $50k obligation from Iowa DOT was reversed - email Mara Kim 8/30/2022
Note on V15: Mohamedali, Mustafa: per Mara email 7/26
Note on V16: Mohamedali, Mustafa: Per Mara email 4/11
Note on R17: Mohamedali, Mustafa: Includes 2019, I assume.
Note on V17: Mohamedali, Mustafa: See Mara email 7/20/22
Note on V18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Obligation expected soon per email JD 3/22
Note on S21: Mohamedali, Mustafa: commitment possible--see email Julian Brad 4/11
Note on T21: Mohamedali, Mustafa: per Mara email 7/26
Note on U21: Mohamedali, Mustafa: commitment possible--see email Julian Brad 4/11
Note on V21: Mohamedali, Mustafa: per Mara email 7/26
Note on V22: Mohamedali, Mustafa: See Michelle Lucas email 5/4/22 Transfer affected per Mara email 5/25/22
Note on U24: Mohamedali, Mustafa: Check received 4/13 - Jon P
Note on V26: Mohamedali, Mustafa: per Mara email 8/23
Note on K27: Mohamedali, Mustafa: obligated but not committed on p/f site
Note on U27: Mohamedali, Mustafa: obligated but not committed on p/f site
Note on V29: Mohamedali, Mustafa: Per Mara email 4/6/22
Note on P31: Mohamedali, Mustafa: $75k obligated for 2019, 2020 and 2021 per Mara email 5/25/22
Note on U32: Mohamedali, Mustafa: Amount by check needed
Note on W35: Mohamedali, Mustafa: 2023 figures not included in calculations or summaries. See Phase 3 tab

## TO's Archived 230906 (hidden)
TPF5-343 and 5-501 Active Task Orders as of: | >>> | 2023-05-31
Figures in red change based on filter applied | >>> | # of T/O's = | 51 |  |  |  | 57.07% |  |  | 7528685 | 3231786.25
Agreement/TO Title | Appr | Fund Type | Contract # | Supp Project | Perf | % time | % Spent | Contract Start Date | Contract End Date | Contract Amount | Contract Balance | Principal Investigator | PI email | Research Agency | SME | SME2 | Main Division | Sub- division | WSDOT Office | Comments
2023 Program Development and Coordination Effort | FED | TPF5501 | T1969-AA |  | 0 | NA | 0% | 2023-05-01 | 2024-04-30 | 50000 | 50000 | Nauman Sheikh | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Optimized Guardrail Blockout | FED | TPF5501 | T1969-AB |  | 0 | NA | 0% | 2023-05-01 | 2024-07-30 | 190100 | 190100 | James Kovar | j-kovar@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
W-Beam Guardrail in Front of Retaining Wall or Rip Rap | FED | TPF5501 | T1969-AC |  | 0 | NA | 0% | 2023-05-01 | 2024-07-31 | 97191 | 97191 |  | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | Erik Emerson ¦ Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Barrier Deflections at lower Impact Severities | FED | TPF5501 | T1969-AD |  | 0 | NA | 0% | 2023-05-01 | 2024-07-31 | 105000 | 105000
Phase 2 Thrie Beam Retrofit - Application of New Design without a Curb for MASH TL-3 and Performance and Improvements for MASH TL-4 | FED | TPF5501 | T1969-AE |  | 0 | NA | 0% | 2023-05-01 | 2024-09-30 |  | 0
MASH TL-3 Evaluation of Sign Posts with Flashing Beacon Equipment | FED | TPF5501 | T1969-AF |  | 0 | NA | 0% | 2023-05-01 | 2024-09-30 | 136018 | 136018
MASH TL-3 Transition Design with a Storm Drain Inlet, Phase II | FED | TPF5501 | T1969-AG |  | 0 | NA | 0% | 2023-05-01 | 2023-12-31 | 76986 | 76986
MINNESOTA ¦ Impact Performance Evaluation of Modified Minnesota Swing-Away Mailbox | LOCAL | TPF5343 ¦ CSR ¦ Local ¦ Minnesota | T4541-CT (MN) ¦ GCB 2588 (MN) |  | 0 | NA | 88% | 2017-10-18 | 2021-10-31 | 181659 | 21695.4 | Roger Bligh | r-bligh@tti.tamu.edu | Texas A & M Transportation Inst | John Donahue | Donahue, John;#30 | Multimodal Development & Delivery | Development Division | Design Office
Testing & Evaluation of the MGS System with the Maximum Flare at MASH TL3 Conditions | TPF | TPF5343 1 | T4541-CV |  | 1.01 | 98% | 100% | 2018-02-01 | 2023-04-30 | 199945 | 743.37 | Chiara Silvestri Dobrovolny, Ph.D | c-silvestri@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Divison | Design Office
Thrie/W-Beam/Tubular Barrier Gap Rail for MASH TL-3 | TPF | TPF5343 1 | T4541-CZ |  | 0.92 | 100% | 92% | 2018-05-01 | 2022-03-31 | 215821 | 18209.03 | William Williams, P.E. | w-williams@tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Divison | Design Office
DESIGN OFFICE ¦ MASH Implementation Technical Support | TPF | TPF5343 ¦ CSR ¦ Design | T4541-DC ¦ Design Office | Design Office | 0.88 | 100% | 88% | 2018-07-01 | 2021-11-30 | 115190 | 13527.8 | Nauman Sheikh | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | John Donahue |  | Multimodal Development & Delivery | Development Division | Design Office
Testing and Evaluation of Large Signs Slipbase Support on Slope at MASH Test Level 3 Impact Conditions | TPF | TPF5343 1 | T4541-DJ |  | 1.02 | 98% | 100% | 2019-03-01 | 2023-01-31 | 183425 | 772.62 | Chiara Silvestri Dobrovolny, Ph.D | c-silvestri@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Divison | Design Office
Shorter TL-3 MASH W-Beam Transition | TPF | TPF5343 | T4541-DO |  | 0.95 | 100% | 95% | 2019-07-16 | 2021-08-31 | 88322 | 4766.52 | Kiana Maysam, Ph.D | m-kiani@tti.tamu.edu | Texas A & M Transportation Inst | John Donahue and Joe Hall | Donahue, John;#30 | Multimodal Development & Delivery | Development Division | Design Office
2019 MASH Coordination Effort | TPF | TPF5343 1 | T4541-DQ |  | 1.04 | 96% | 99% | 2019-08-01 | 2021-07-31 | 65000 | 530.66 | Chiara Silvestri Dobrovolny, Ph.D | c-silvestri@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
A Study of Acceptable Sidewalk Heights and Widths | TPF | TPF5343 1 | T4541-DV |  | 1 | 100% | 100% | 2019-12-16 | 2022-01-31 | 150154 | 294.31 | Akram Abu-Odeh | a-abu-odeh@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Design and Testing of a Thrie-beam Guardrail System at a Fixed Object | TPF | TPF5343 1 | T4541-DW |  | 0.99 | 100% | 99% | 2019-12-16 | 2022-03-31 | 176184 | 1324.64 | James Kovar, E.I.T. | j-kovar@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Design and Testing of a MASH TL-3 Thrie-Beam System for Roadside and Median Applications | TPF | TPF5343 1 | T4541-DX |  | 0.8 | 100% | 80% | 2020-03-01 | 2022-01-31 | 258780 | 51938.03 | Maysam Kiani | m-kiani@tti.tamu.edu | Texas A & M Transportation Inst | James Danila (MassDOT)/Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
MASH TL-3 Transition Design with a Storm Drain Inlet | TPF | TPF5343 1 | T4541-DY |  | 1.06 | 91% | 96% | 2020-10-01 | 2023-06-30 | 253110 | 9782.15 | Akram Abu-Odeh | a-abu-odeh@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel ¦ Derwood Sheppard | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Determination of the Length-of-Need for Guardrail without Anchorage Phase 2: MASH Crash Testing | TPF | TPF5343 1 | T4541-DZ |  | 0.91 | 100% | 91% | 2020-11-01 | 2023-01-15 | 131269 | 12334.57 | James Kovar, E.I.T. | j-kovar@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Development of A Thrie-Beam Retrofit for Upgrading Obsolete Bridge Railings | TPF | TPF5343 | T4541-EA |  | 0.98 | 100% | 98% | 2020-09-01 | 2021-12-31 | 227675 | 3787.52 | William Williams, P.E. | w-williams@tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
2021 Administrative Support | TPF | TPF5343 | T4541-EB |  | 0.9 | 100% | 90% | 2021-01-01 | 2022-08-31 | 20602 | 2130.47 | Chiara Silvestri Dobrovolny, Ph.D | c-silvestri@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Development and Evaluation of a Non-Proprietary Sign Support System for MASH Test Level 3 Conditions | TPF | TPF5343 | T4541-EC |  | 0.67 | 96% | 64% | 2021-02-15 | 2023-05-31 | 165305 | 59175.56 | Nathan Schultz | n-schulz@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Guidelines for Attaching MASH-compliant Thrie Beam Transitions to Rigid Concrete Barriers other than the Rigid Barrier Tested | TPF | TPF5343 1 | T4541-ED |  | 1.06 | 93% | 99% | 2021-02-15 | 2023-06-30 | 92613 | 1061.64 | Roger Bligh | R-Bligh@tti.tamu.edu | Texas A & M Transportation Inst | Jeff C Jeffers/Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
An Exploration into Variations in Guardrail Approach Transitions to Rigid Barrier | FED | TPF5343 | T4541-EE |  | 1 | 100% | 100% | 2021-02-15 | 2023-02-15 | 86299 | 0.01 | Maysam Kiani | m-kiani@tti.tamu.edu | Texas A & M Transportation Inst | Erik Emerson/Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States | TPF | TPF5343 | T4541-EF |  | 1.04 | 96% | 100% | 2021-02-01 | 2022-02-15 | 50000 | 101.92 | William Williams, P.E. | w-williams@tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
2021 Program Development and MASH Coordination Effort | TPF | TPF5343 | T4541-EG |  | 1 | 100% | 100% | 2021-03-16 | 2022-12-31 | 65000 | 13.95 | Chiara Silvestri Dobrovolny, Ph.D | c-silvestri@tti.tamu.edu | Texas A & M Transportation Inst | Jeff C Jeffers/Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
ILLINOIS ¦MASH TL-4 Crash Testing of Bicycle Railing on Constant Slope Parapet | TPF | TPF5343 | T4541-EH | IL | 0.64 | 100% | 64% | 2021-03-22 | 2022-02-28 | 248886 | 90571.57 | Maysam Kiani | m-kiani@tti,tamu.edu | Texas A & M Transportation Inst | Tim Craven (Illinois DOT) | Donahue, John;#30 | Multimodal Development & Delivery | Development Division | Design Office
FLORIDA ¦Crashworthy Enhanced Highway Signb Assemblies | TPF | TPF5343 ¦ CSR ¦ Florida | T4541-EI | FL | 0.7 | 93% | 65% | 2021-03-22 | 2023-06-30 | 175877 | 61454.04 | Maysam Kiani | m-kiani@tti,tamu.edu | Texas A & M Transportation Inst | Derwood Sheppard ¦ Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
FLORIDA ¦Design and Evaluation of a MASH Test Level 2 Compliant Permanent Concrete Low Profile Barrier | TPF | TPF5343 ¦ CSR ¦ Florida | T4541-EJ | FL | 0.92 | 100% | 92% | 2021-03-22 | 2022-08-31 | 165985 | 12754.71 | Chiara Silvestri Dobrovolny, Ph.D | c-silvestri@tti.tamu.edu | Texas A & M Transportation Inst | Derwood Sheppard / John Donahue | Donahue, John;#30 | Multimodal Development & Delivery | Development Division | Design Office
Transition between Guardrail and Tangent Anchored Portable Concrete Barriers | TPF | TPF5343 | T4541-EK |  | 0.88 | 100% | 88% | 2021-05-16 | 2022-11-30 | 200925 | 23693.64 | Nauman Sheikh | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | Shawn Debanham Utah DOT/ John Donahue | Donahue, John;#30 | Multimodal Development & Delivery | Development Division | Design Office
Testing Type III Barricades with Mounted Signs | TPF | TPF5343 | T4541-EL |  | 0.73 | 100% | 73% | 2021-06-01 | 2022-11-30 | 178687 | 47416.82 | James Kovar, E.I.T. | j-kovar@tti.tamu.edu | Texas A & M Transportation Inst | Brian Crossley/Hassan Raza PA DOT/ John Donahue | Donahue, John;#30 | Multimodal Development & Delivery | Development Division | Design Office
Multi-directional Base Design for Steel Beam Non-proprietary Large Sign | TPF | TPF5343 1 | T4541-EM |  | 0.3 | 76% | 23% | 2021-06-01 | 2023-12-01 | 405501 | 311924.97 | James Kovar, E.I.T. | j-kovar@tti.tamu.edu | Texas A & M Transportation Inst | Ted Whitmore WVDOT/Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Development of a MASH TL-3 Compliant Portable Concrete Barrier System | LOCAL | TPF5343 ¦ Local | T4541-EN | CA | 1.02 | 68% | 69% | 2021-09-01 | 2023-12-31 | 442654 | 138426.37 | Nauman Sheikh | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | Bob Meline Caltrans ¦ Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
SCR ¦Washington State I-90 Snoqualmie Pass Barrier Gap Design, Drafting, and Detailing | TPF | TPF5343 ¦ CSR ¦ SCR | T4541-EO | SCR | 0.98 | 100% | 98% | 2021-10-16 | 2022-04-15 | 20043 | 354.97 | William Williams, P.E. | w-williams@tamu.edu | Texas A & M Transportation Inst | John Donahue |  | Multimodal Development & Delivery | Development Division | Design Office
WA ¦ Evaluation of Long-Span W-Beam Guardrail in Front of Fall-Protection Rail on Concrete Culverts | TPF | TPF5343 ¦ CSR ¦ ESO Fish Passage Proigram | T4541-EP | ESO | 1.13 | 89% | 100% | 2022-01-01 | 2023-06-30 | 220173 | 2.12 | Nauman Sheikh PE | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
2022 Program Development and MASH Coordination Effort | TPF | TPF5343 | T4541-EQ |  | 1.49 | 50% | 74% | 2022-05-01 | 2023-12-31 | 50000 | 12914.1 | Chiara Silvestri Dobrovolny | c-silvestri@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Divison | Design Office
Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States | TPF | TPF5343 | T4541-ER |  | 1.98 | 45% | 90% | 2022-05-01 | 2023-12-31 | 55000 | 5742.93 | Nauman Sheikh | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | James Danila (MassDOT) ¦ Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Divison | Design Office
MASH 4-12 Evaluation of a Fence Mounted System for Attachments to Concrete Bridge Barrier | TPF | TPF5343 | T4541-ES |  | 0.5 | 61% | 30% | 2022-06-01 | 2023-11-30 | 175463 | 122461.13 | Maysam Kiani, Ph.D., P.E., PMP | m-kiani@tti.tamu.edu | Texas A & M Transportation Inst | Derwood Sheppard ¦ Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Divison | Design Office
MASH Testing of a Guardrail System on 1H:1V Slope | TPF | TPF5343 1 | T4541-ET |  | 0.23 | 80% | 19% | 2022-05-01 | 2023-07-31 | 173907 | 141561.24 | Akram Abu-Odeh | a-abu-odeh@tti.tamu.edu | Texas A & M Transportation Inst | Ted Whitmore WVDOT/Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Divison | Design Office
Funding for Strain Gauge Deck and Barrier Optimization for Roadside Safety Issues/Problems for Member States | TPF | TPF5343 ¦ CSR ¦ CDOT | T4541-EU | CO | 0.57 | 91% | 52% | 2022-06-01 | 2023-05-31 | 40000 | 19101.53 | William Williams | w-williams@tti.tamu.edu | Texas A & M Transportation Inst | John Donahue and Andy Pott | Donahue, John;#30 | Multimodal Development & Delivery | Development Divison | Design Office
MASH Crashworthy Pedestrian and Small Traffic Signals | TPF | TPF5343 | T4541-EV |  | 0.33 | 64% | 21% | 2022-06-01 | 2023-10-31 | 215134 | 169429.17 | Sofokli Cakalli | s-cakalli@tti.tamu.edu | Texas A & M Transportation Inst | Derwood Sheppard ¦ Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
2022 Administrative Support | TPF | TPF5343 | T4541-EW |  | 0.37 | 83% | 30% | 2022-07-01 | 2023-06-30 | 19488 | 13557.05 | Nauman Sheikh | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Buried-in-Backslope Terminal Variations in Foreslope, Backslope, and Ditch Configurations | LOCAL | TPF5343 | T4541-EX |  | 0.64 | 69% | 44% | 2022-06-01 | 2023-09-30 | 90994 | 50787.5 | Sofokli Cakalli | s-cakalli@tti.tamu.edu | Texas A & M Transportation Inst | Mary McRae, P.E. and Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Washington State I-90 Snoqualmie Pass Scupper Barrier Full-Scale Crash Testing | TPF | TPF5343 ¦ CSR ¦ SCR | T4541-EY | SCR | 0.15 | 66% | 10% | 2022-09-01 | 2023-08-31 | 188899 | 170160.97 | William Williams | w-williams@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Divison | Design Office
2022 Meeting and Travel Assistance | TPF | TPF5343 1 | T4541-EZ |  | 0.55 | 100% | 55% | 2022-08-01 | 2023-02-28 | 99653 | 44676.8 | Roger Bligh | r-bligh@tt.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel |  | Multimodal Development & Delivery | Development Divison | Design Office
Opinion on MASH Compliance of WSDOT's 42-lnch Tall Prep-Cast F-Shape Barrier | TPF | TPF5343 ¦ CSR ¦ Design | T4541-FA |  | 1 | 100% | 100% | 2022-10-01 | 2022-12-31 | 3890 | 17.89 | Nauman M. Sheikh, P.E. | n-sheikh@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
MASH TL-3 Evaluation of Median Guide Rail Transition to Median F-Shape Concrete Barrier | LOCAL | TPF5343 ¦ Local | T4541-FB |  | 0.14 | 40% | 6% | 2022-11-16 | 2023-12-31 | 180057 | 170009.05 | Nathan D. Schulz, Ph.D. | n-schulz@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Evaluation of a Four Bolt Slip Base for Breakaway Luminaire Supports with Various Pole Configurations | LOCAL | TPF5343 | T4541-FC |  | 0.1 | 40% | 4% | 2022-12-01 | 2023-12-15 | 219681 | 210798.91 | James Kovar | j-kovar@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Portable Sign Supports for Aluminum Signs with Variations on Mounting Height | LOCAL | TPF5343 ¦ Local | T4541-FD |  | 0.09 | 40% | 4% | 2022-12-01 | 2023-12-15 | 208145 | 200416.82 | James Kovar | j-kovar@tti.tamu.edu | Texas A & M Transportation Inst | Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
MASH Test Level 3 Evaluation of a Shorter Thrie-Beam Approach Transition | LOCAL | TPF5343 ¦ Local | T4541-FE |  | 0.21 | 36% | 7% | 2022-12-15 | 2023-12-31 | 135772 | 125661.68 | Maysam Kiani | m-kiani@tti.tamu.edu | Texas A & M Transportation Inst | Ted Whitmore WVDOT/Tim Moeckel | Moeckel, Tim;#32 | Multimodal Development & Delivery | Development Division | Design Office
Steel-Post W-Beam Guardrail in Asphalt Mow-Strip | FED | TPF5343 1 | T4541-FF |  | 0.14 | 5% | 1% | 2023-04-16 | 2023-12-31 | 232223 | 230405.1 |  |  | Texas A & M Transportation Inst

## TO's 5-343 & 5-501
RMs Spreadsheet - MM |  | 2023-09-06 | [8 empty] | Months remaining (incl Jul) |  | 6
[11 empty] | Reqd burn rate to end Dec'23 |  | 301294.0917
|  |  | 54 | (total t/o's) | 17 | (filtered t/o's) |  |  |  |  | Subtotals | 2890873 | 1807764.55
BN | Title | Agreement/TO Title | Appropriation | Fund Type | Contract # | Supp | Perf | % time elapsed | % Spent on Project (Actual Exp/Project Amt) | Start | End | Amount | Balance | PI | Instit'n | SME | Org | Div | Office | WA-RD#
21-23 | TPF5501 Roadside Safety Pooled Fund- Phase 3 | Phase 2 Thrie Beam Retrofit - Application of New Design without a Curb for MASH TL-3 and Performance and Improvements for MASH TL-4 | FED | TPF5501 | T1969-AE |  | 0.45165 | 17.57% | 7.934% | 2023-05-01 | 2024-09-30 | 159441 | 146790.24 | William Williams | Texas A & M Transportation Inst | Carlos Torres ¦ Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | TPF5501 Roadside Safety Pooled Fund- Phase 3 | MASH TL-3 Evaluation of Sign Posts with Flashing Beacon Equipment | FED | TPF5501 | T1969-AF |  | 0.10289 | 11.58% | 1.192% | 2023-05-01 | 2024-09-30 | 136018 | 134396.91 | Nathan D. Schulz, Ph.D. | Texas A & M Transportation Inst | Flint Jackson ¦ Tim Moeckel | Multimodal Development & Delivery | Development Division | Traffic Office ¦ Design Office
21-23 | TPF5501 Roadside Safety Pooled Fund- Phase 3 | W-Beam Guardrail in Front of Retaining Wall or Rip Rap | FED | TPF5501 | T1969-AC |  | 0.16295 | 19.91% | 3.245% | 2023-05-01 | 2024-07-31 | 97191 | 94037.49 | Nauman Sheikh | Texas A & M Transportation Inst | Erik Emerson ¦ Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | TPF5501 Roadside Safety Pooled Fund- Phase 3 | Barrier Deflections at lower Impact Severities | FED | TPF5501 | T1969-AD |  | 0.24223 | 19.91% | 4.823% | 2023-05-01 | 2024-07-31 | 105000 | 99935.42 | James Kovar | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | TPF5501 Roadside Safety Pooled Fund - Phase 3 | Optimized Guardrail Blockout | FED | TPF5501 | T1969-AB |  | 0.15586 | 19.96% | 3.11% | 2023-05-01 | 2024-07-30 | 190100 | 184187.35 | James Kovar | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | TPF5501 Roadside Safety Pooled Fund- Phase 3 | 2023 Program Development and Coordination Effort | FED | TPF5501 | T1969-AA |  | 0.018179 | 16.44% | 0.2988% | 2023-05-01 | 2024-04-30 | 50000 | 49850.58 | Nauman Sheikh | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
23-25 | TPF5501 | U1969-AI (CO) Design and MASH Full-Scale Crash Testing and Evaluation of the Merritt Parkway Guiderail | FED | TPF5501 1 | U1969-AI |  | 0 | NA | 0% | 2023-09-01 | 2024-04-30 | 544795 | 544795
23-25 | 2023 Travel and Meeting Assistance | 2023 Travel and Meeting Assistance | FED | TPF5501 1 | T1969-AH |  | 0 | NA | 0% | 2023-08-01 | 2024-02-29 | 112063 | 112063
21-23 | TPF5501 Roadside Safety Pooled Fund- Phase 3 | MASH TL-3 Transition Design with a Storm Drain Inlet, Phase II | FED | TPF5501 | T1969-AG |  | 1.9495 | 37.3% | 72.71% | 2023-05-01 | 2023-12-31 | 76986 | 21012.94 | Akram Abu-Odeh | Texas A & M Transportation Inst | Derwood Sheppard ¦ Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | Roadside Safety Research for MASH Implementation | MINNESOTA ¦ Impact Performance Evaluation of Modified Minnesota Swing-Away Mailbox | LOCAL | TPF5343 ¦ CSR ¦ Local ¦ Minnesota | T4541-CT (MN) ¦ GCB 2588 (MN) |  | 0 | NA | 88.06% | 2017-10-18 | 2021-10-31 | 181659 | 21695.4 | Roger Bligh | Texas A & M Transportation Inst | John Donahue | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Portable Sign Supports for Aluminum Signs with Variations on Mounting Height | Portable Sign Supports for Aluminum Signs with Variations on Mounting Height | LOCAL | TPF5343 ¦ Local | T4541-FD |  | 0.10215 | 63.85% | 6.522% | 2022-12-01 | 2023-12-15 | 208145 | 194569.25 | James Kovar | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Evaluation of a Four Bolt Slip Base for Breakaway Luminaire Supports with Various Pole Configurations | Evaluation of a Four Bolt Slip Base for Breakaway Luminaire Supports with Various Pole Configurations | LOCAL | TPF5343 | T4541-FC |  | 0.11618 | 63.85% | 7.418% | 2022-12-01 | 2023-12-15 | 219681 | 203384.94 | James Kovar | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | MASH TL-3 Evaluation of Median Guide Rail Transition to Median F-Shape Concrete Barrier | MASH TL-3 Evaluation of Median Guide Rail Transition to Median F-Shape Concrete Barrier | LOCAL | TPF5343 ¦ Local | T4541-FB |  | 0.14988 | 62.68% | 9.395% | 2022-11-16 | 2023-12-31 | 180057 | 163140.39 | Nathan D. Schulz, Ph.D. | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Washington State I-90 Snoqualmie Pass Scupper Barrier Full-Scale Crash Testing | Washington State I-90 Snoqualmie Pass Scupper Barrier Full-Scale Crash Testing | TPF | TPF5343 ¦ CSR ¦ SCR | T4541-EY | SCR | 0.15963 | 62.14% | 9.92% | 2022-09-01 | 2023-12-31 | 188899 | 170160.97 | William Williams | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | Evaluation of Open Joints in Concrete Bridge Rail Systems | Evaluation of Open Joints in Concrete Bridge Rail Systems | FED | TPF5343 1 | T4541-FG |  | 0.17844 | 18.94% | 3.38% | 2023-05-18 | 2023-12-31 | 47955 | 46334.09 | Nathan D. Schulz, Ph.D. | Texas A & M Transportation Inst | Alex Lim ¦ Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | MASH Test Level 3 Evaluation of a Shorter Thrie-Beam Approach Transition | MASH Test Level 3 Evaluation of a Shorter Thrie-Beam Approach Transition | LOCAL | TPF5343 ¦ Local | T4541-FE |  | 0.23754 | 59.84% | 14.22% | 2022-12-15 | 2023-12-31 | 135772 | 116471.82 | William Williams | Texas A & M Transportation Inst | Ted Whitmore WVDOT/Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | MASH Crashworthy Pedestrian and Small Traffic Signals | MASH Crashworthy Pedestrian and Small Traffic Signals | TPF | TPF5343 | T4541-EV |  | 0.3524 | 73.53% | 25.91% | 2022-06-01 | 2023-12-31 | 215134 | 159388.45 | Sofokli Cakalli | Texas A & M Transportation Inst | Derwood Sheppard ¦ Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | TPF5343 Roadside Safety for MASH Implementation | Steel-Post W-Beam Guardrail in Asphalt Mow-Strip | FED | TPF5343 1 | T4541-FF |  | 0.39621 | 40.93% | 16.22% | 2023-04-16 | 2023-12-31 | 232223 | 194567.07 | Nauman M. Sheikh, P.E. | Texas A & M Transportation Inst | Christopher Lindsey, P.E. ¦ Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Multi-directional Base Design for Steel Beam Non-proprietary Large Sign | TPF | TPF5343 1 | T4541-EM |  | 0.51515 | 86.53% | 44.57% | 2021-06-01 | 2023-12-01 | 405501 | 224751.16 | James Kovar, E.I.T. | Texas A & M Transportation Inst | Ted Whitmore WVDOT/Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | 2022 Meeting and Travel Assistance | 2022 Meeting and Travel Assistance | TPF | TPF5343 1 | T4541-EZ |  | 0.55168 | 100% | 55.17% | 2022-08-01 | 2023-02-28 | 99653 | 44676.8 | Roger Bligh | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | MASH 4-12 Evaluation of a Fence Mounted System for Attachments to Concrete Bridge Barrier | MASH 4-12 Evaluation of a Fence Mounted System for Attachments to Concrete Bridge Barrier | TPF | TPF5343 | T4541-ES |  | 0.57128 | 77.7% | 44.39% | 2022-06-01 | 2023-11-30 | 175463 | 97581.47 | Maysam Kiani, Ph.D., P.E., PMP | Texas A & M Transportation Inst | Derwood Sheppard ¦ Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | Roadside Safety Research for MASH Implementation | ILLINOIS ¦MASH TL-4 Crash Testing of Bicycle Railing on Constant Slope Parapet | TPF | TPF5343 | T4541-EH | IL | 0.63609 | 100% | 63.61% | 2021-03-22 | 2022-02-28 | 248886 | 90571.57 | Maysam Kiani | Texas A & M Transportation Inst | Tim Craven (Illinois DOT) | Multimodal Development & Delivery | Development Division | Design Office
21-23 | MASH Testing of a Guardrail System on 1H:1V Slope | MASH Testing of a Guardrail System on 1H:1V Slope | TPF | TPF5343 | T4541-ET |  | 0.69433 | 93.2% | 64.71% | 2022-05-01 | 2023-07-31 | 173907 | 61367.25 | Akram Abu-Odeh | Texas A & M Transportation Inst | Ted Whitmore WVDOT/Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Testing Type III Barricades with Mounted Signs | TPF | TPF5343 | T4541-EL |  | 0.73464 | 100% | 73.46% | 2021-06-01 | 2022-11-30 | 178687 | 47416.82 | James Kovar, E.I.T. | Texas A & M Transportation Inst | Brian Crossley/Hassan Raza PA DOT/ John Donahue | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Design and Testing of a MASH TL-3 Thrie-Beam System for Roadside and Median Applications | FED | TPF5343 1 | T4541-DX |  | 0.7993 | 100% | 79.93% | 2020-03-01 | 2022-01-31 | 258780 | 51938.03 | Maysam Kiani | Texas A & M Transportation Inst | James Danila (MassDOT)/Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Buried-in-Backslope Terminal Variations in Foreslope, Backslope, and Ditch Configurations | Buried-in-Backslope Terminal Variations in Foreslope, Backslope, and Ditch Configurations | LOCAL | TPF5343 | T4541-EX |  | 0.80507 | 73.53% | 59.2% | 2022-06-01 | 2023-12-31 | 90994 | 37129.23 | Sofokli Cakalli | Texas A & M Transportation Inst | Mary McRae, P.E. and Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Development and Evaluation of a Non-Proprietary Sign Support System for MASH Test Level 3 Conditions | TPF | TPF5343 | T4541-EC |  | 0.81214 | 100% | 81.21% | 2021-02-15 | 2023-05-31 | 165305 | 31053.8 | Nathan Schultz | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Funding for Strain Gauge Deck and Barrier Optimization for Roadside Safety Issues/Problems for Member States | Funding for Strain Gauge Deck and Barrier Optimization for Roadside Safety Issues/Problems for Member States | TPF | TPF5343 ¦ CSR ¦ CDOT | T4541-EU | CO | 0.83174 | 68.17% | 56.7% | 2022-06-01 | 2023-12-31 | 40000 | 17321.37 | William Williams | Texas A & M Transportation Inst | John Donahue and Andy Pott | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | FLORIDA ¦Crashworthy Enhanced Highway Signb Assemblies | FLORIDA ¦Crashworthy Enhanced Highway Signb Assemblies | TPF | TPF543 ¦ CSR ¦ Florida | T4541-EI | FL | 0.67997 | 96.39% | 65.54% | 2021-03-22 | 2023-06-30 | 175877 | 60608.04 | Maysam Kiani | Texas A & M Transportation Inst | Derwood Sheppard ¦ Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Transition between Guardrail and Tangent Anchored Portable Concrete Barriers | TPF | TPF5343 | T4541-EK |  | 0.88208 | 100% | 88.21% | 2021-05-16 | 2022-11-30 | 200925 | 23693.64 | Nauman Sheikh | Texas A & M Transportation Inst | Shawn Debanham Utah DOT/ John Donahue | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | DESIGN OFFICE ¦ MASH Implementation Technical Support | TPF | TPF5343 ¦ CSR ¦ Design | T4541-DC ¦ Design Office | Design Office | 0.88256 | 100% | 88.26% | 2018-07-01 | 2021-11-30 | 115190 | 13527.8 | Nauman Sheikh | Texas A & M Transportation Inst | John Donahue | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | 2021 Administrative Support | TPF | TPF5343 | T4541-EB |  | 0.89659 | 100% | 89.66% | 2021-01-01 | 2022-08-31 | 20602 | 2130.47 | Chiara Silvestri Dobrovolny, Ph.D | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Determination of the Length-of-Need for Guardrail without Anchorage Phase 2: MASH Crash Testing | FED | TPF5343 1 | T4541-DZ |  | 0.90604 | 100% | 90.6% | 2020-11-01 | 2023-01-15 | 131269 | 12334.57 | James Kovar, E.I.T. | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Thrie/W-Beam/Tubular Barrier Gap Rail for MASH TL-3 | FED | TPF5343 1 | T4541-CZ |  | 0.91563 | 100% | 91.56% | 2018-05-01 | 2022-03-31 | 215821 | 18209.03 | William Williams, P.E. | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Development of a MASH TL-3 Compliant Portable Concrete Barrier System | LOCAL | TPF5343 ¦ Local | T4541-EN | CA | 0.93982 | 82.02% | 77.09% | 2021-09-01 | 2023-12-31 | 442654 | 101432.23 | Nauman Sheikh | Texas A & M Transportation Inst | Bob Meline Caltrans ¦ Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Shorter TL-3 MASH W-Beam Transition | TPF | TPF5343 | T4541-DO |  | 0.94603 | 100% | 94.6% | 2019-07-16 | 2021-08-31 | 88322 | 4766.52 | Kiana Maysam, Ph.D | Texas A & M Transportation Inst | John Donahue and Joe Hall | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | SCR ¦Washington State I-90 Snoqualmie Pass Barrier Gap Design, Drafting, and Detailing | TPF | TPF5343 ¦ CSR ¦ SCR | T4541-EO | SCR | 0.98229 | 100% | 98.23% | 2021-10-16 | 2022-04-15 | 20043 | 354.97 | William Williams, P.E. | Texas A & M Transportation Inst | John Donahue | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Development of A Thrie-Beam Retrofit for Upgrading Obsolete Bridge Railings | FED | TPF5343 | T4541-EA |  | 0.98336 | 100% | 98.34% | 2020-09-01 | 2021-12-31 | 227675 | 3787.52 | William Williams, P.E. | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | MASH TL-3 Transition Design with a Storm Drain Inlet | FED | TPF5343 1 | T4541-DY |  | 0.98725 | 100% | 98.73% | 2020-10-01 | 2023-06-30 | 253110 | 3225.96 | Akram Abu-Odeh | Texas A & M Transportation Inst | Tim Moeckel ¦ Derwood Sheppard | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Design and Testing of a Thrie-beam Guardrail System at a Fixed Object | FED | TPF5343 1 | T4541-DW |  | 0.99248 | 100% | 99.25% | 2019-12-16 | 2022-03-31 | 176184 | 1324.64 | James Kovar, E.I.T. | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Opinion on MASH Compliance of WSDOT's 42-lnch Tall Prep-Cast F-Shape Barrier | Opinion on MASH Compliance of WSDOT's 42-lnch Tall Prep-Cast F-Shape Barrier | TPF | TPF5343 ¦ CSR ¦ Design | T4541-FA |  | 0.9954 | 100% | 99.54% | 2022-10-01 | 2022-12-31 | 3890 | 17.89 | Nauman M. Sheikh, P.E. | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | FLORIDA ¦Design and Evaluation of a MASH Test Level 2 Compliant Permanent Concrete Low Profile Barrier | TPF | TPF543 ¦ CSR ¦ Florida | T4541-EJ | FL | 0.92316 | 100% | 92.32% | 2021-03-22 | 2022-08-31 | 165985 | 12754.71 | Chiara Silvestri Dobrovolny, Ph.D | Texas A & M Transportation Inst | Derwood Sheppard / John Donahue | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | A Study of Acceptable Sidewalk Heights and Widths | FED | TPF5343 1 | T4541-DV |  | 0.99804 | 100% | 99.8% | 2019-12-16 | 2022-01-31 | 150154 | 294.31 | Akram Abu-Odeh | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Testing and Evaluation of Large Signs Slipbase Support on Slope at MASH Test Level 3 Impact Conditions | FED | TPF5343 1 | T4541-DJ |  | 0.99847 | 100% | 99.85% | 2019-03-01 | 2023-01-31 | 183425 | 280.87 | Chiara Silvestri Dobrovolny, Ph.D | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | Roadside Safety Research for MASH Implementation | 2021 Program Development and MASH Coordination Effort | TPF | TPF5343 | T4541-EG |  | 0.99979 | 100% | 99.98% | 2021-03-16 | 2022-12-31 | 65000 | 13.95 | Chiara Silvestri Dobrovolny, Ph.D | Texas A & M Transportation Inst | Jeff C Jeffers/Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Guidelines for Attaching MASH-compliant Thrie Beam Transitions to Rigid Concrete Barriers other than the Rigid Barrier Tested | TPF | TPF5343 1 | T4541-ED |  | 0.9998 | 100% | 99.98% | 2021-02-15 | 2023-06-30 | 92613 | 18.86 | Roger Bligh | Texas A & M Transportation Inst | Jeff C Jeffers/Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | An Exploration into Variations in Guardrail Approach Transitions to Rigid Barrier | FED | TPF5343 | T4541-EE |  | 1 | 100% | 100% | 2021-02-15 | 2023-02-15 | 86299 | 0.01 | Maysam Kiani | Texas A & M Transportation Inst | Erik Emerson/Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Testing & Evaluation of the MGS System with the Maximum Flare at MASH TL3 Conditions | FED | TPF5343 1 | T4541-CV |  | 1 | 100% | 100% | 2018-02-01 | 2023-04-30 | 199945 | 0 | Chiara Silvestri Dobrovolny, Ph.D | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | Roadside Safety Research for MASH Implementation | 2019 MASH Coordination Effort | FED | TPF5343 1 | T4541-DQ |  | 1.0358 | 95.75% | 99.18% | 2019-08-01 | 2021-07-31 | 65000 | 530.657 | Chiara Silvestri Dobrovolny, Ph.D | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States | TPF | TPF5343 | T4541-EF |  | 1.0391 | 96.04% | 99.8% | 2021-02-01 | 2022-02-15 | 50000 | 101.92 | William Williams, P.E. | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
23-25 | TPF5343 Roadside Safety Research for MASH Implementation | 2022 Administrative Support | FED | TPF5343 1 | T4541-EW |  | 1.043 | 66.42% | 69.28% | 2022-07-01 | 2023-12-31 | 19488 | 4854.82 | Nauman Sheikh | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Roadside Safety Research for MASH Implementation | WA ¦ Evaluation of Long-Span W-Beam Guardrail in Front of Fall-Protection Rail on Concrete Culverts | TPF | TPF5343 ¦ CSR ¦ ESO Fish Passage Proigram | T4541-EP | ESO | 1.126 | 88.81% | 100% | 2022-01-01 | 2023-06-30 | 220173 | 2.12 | Nauman Sheikh PE | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Division | Design Office
21-23 | Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States | Engineering Support Services and Recommendations for Roadside Safety Issues/Problems for Member States | TPF | TPF5343 | T4541-ER |  | 1.2164 | 69.79% | 84.89% | 2022-05-01 | 2023-12-31 | 65000 | 9822.18 | Nauman Sheikh | Texas A & M Transportation Inst | James Danila (MassDOT) ¦ Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office
21-23 | 2022 Program Development and MASH Coordination | 2022 Program Development and MASH Coordination Effort | TPF | TPF5343 | T4541-EQ |  | 1.2757 | 69.79% | 89.02% | 2022-05-01 | 2023-12-31 | 50000 | 5487.86 | Nauman M. Sheikh, P.E. | Texas A & M Transportation Inst | Tim Moeckel | Multimodal Development & Delivery | Development Divison | Design Office

## 5-501 (Phase 3)
TPF5-(501) Phase 3 |  | Committed vs Obligated Status |  | v.230726 | updated commitments |  |  |  | commitment amount in $1,000's |  |  |  |  | y = | obligated | n = | not obligated
ID# | Organization | Technical Contact Name | Funding Contact Name | Contact Number | Email Address | Commited | Obligated | Ph.3? | 2023 | Obl | 2024 | Obl | 2025 | Obl | 2026 | Obl | 2027 | Obl
1 | Alabama DOT | Wade Henry | Kidada Dixon | 334-353-6944 | dixonk@dot.state.al.us | 130 | 130 | C | 65 | y | 65 | y
2 | Alaska DOT and Public Facilities | Mary McRae | Anna Bosin | (907)269-6208 | anna.bosin@alaska.gov | 130 | 65 | C | 65 | y | 65
3 | California DOT | John Jewell | Sang Le | (916)701-3998 | sang.le@dot.ca.gov | 130 | 65 | C | 65 | y | 65
4 | Colorado DOT | Andy Pott | David Reeves | 303-757-9518 | david.reeves@state.co.us | 145 | 65 | C | 15 | y | 65 |  | 65
5 | Connecticut DOT | David Kilpatrick | Melanie Zimyeski | (860)594-2144 | Melanie.Zimyeski@ct.gov | 195 | 65 | C | 65 | y | 65 |  | 65
6 | Delaware DOT | Craig Blowers | Nicole Johnson | 302-760-2092 | nicole.johnson@delaware.gov | 130 | 130 | C | 65 | y | 65 | y
7 | Florida DOT | Derwood Sheppard | Jennifer Clark | 850-414-4614 | jennifer.clark@dot.state.fl.us | 195 | 65 | C | 65 | y | 65 |  | 65
8 | Idaho DOT | Marc Danley | Ned Parrish | 208-334-8296 | ned.parrish@itd.idaho.gov | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
9 | Illinois DOT | Martha Brown | Megan Swanson | 217-782-3547 | Megan.Swanson@illinois.gov | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
10 | Iowa DOT | Daniel Harness | Chris Anderson | 515-239-1819 | christie.anderson@iowadot.us | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
11 | Louisiana DOT and Development | Chris Guidry | Tyson Rupnow | 225-767-9124 | tyson.rupnow@la.gov | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
12 | Maryland DOT | Matamba Kabengele | Sharon Hawkins | 410-545-2920 | shawkins2@mdot.maryland.gov | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
13 | Massachusetts DOT | James Danila | Lily Oliver | (857)368-9025 | hongyan.oliver@state.ma.us | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
14 | Michigan DOT | Carlos Torres | Andre' Clover | 517-749-9001 | clovera@michigan.gov | 195 | 65 | C | 65 | y | 65 |  | 65
15 | Minnesota DOT | Khamsai Yang | Nicole Westadt | 651-366-4270 | nicole.westadt@state.mn.us | 195 | 65 | C | 65 | y | 65 |  | 65
16 | Mississippi DOT | Heath Patterson | Robert Vance |  | RVance@mdot.ms.gov | 0 | 0 | N
17 | Missouri DOT | Sarah Kleinschmit | Jennifer Harper | 573-526-3636 | Jennifer.Harper@modot.mo.gov | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
18 | New Mexico DOT | Brad Julian | Angelo Armijo | (505)372-8757 | Angelo.Armijo@dot.nm.gov | 130 | 65 | C | 65 | y | 65
19 | Ohio DOT | Don Fisher | General Research | 614-644-8135 | Research@dot.state.oh.us | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
20 | Oklahoma DOT | Hebret Bokhru | Ron Curb | (405)420-9163 | rcurb@odot.org | 0 | 0 | N
21 | Ontario MOT | Kenneth Shannon | Joel Magnan | 416-420-0964 | joel.magnan@ontario.ca | 195 | 65 | C | 65 | y | 65 |  | 65
22 | Oregon DOT | Heidi Shoblom | Michael Bufalino | 503-986-2845 | Michael.Bufalino@odot.state.or.us | 130 | 130 | C | 65 | y | 65 | y
23 | Pennsylvania DOT | Evan Pursel | Heather Sorce | 717-214-9508 | hsorce@pa.gov | 195 | 65 | C | 65 | y | 65 |  | 65
24 | Rhode Island DOT |  |  |  |  | 0 | 0 | E
25 | Tennessee DOT | Ali Hangul | Melanie Murphy | 615-253-2158 | melanie.murphy@tn.gov | 195 | 65 | C | 65 | y | 65 |  | 65
26 | Texas DOT | Christopher Lindsey | Ned Mattila | 512-416-4727 | ned.mattila@txdot.gov | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
27 | Utah DOT | Shawn Debenham | David Stevens | 801-589-8340 | davidstevens@utah.gov | 195 | 65 | C | 65 | y | 65 |  | 65
28 | Washington State DOT | Tim Moeckel | Mustafa Mohamedali | 360-704-6307 | MOHAMEM@wsdot.wa.gov | 97.5 | 65 | C | 32.5 | y | 32.5 |  | 32.5
29 | West Virginia DOT | Ted Whitmore | Perry Keller | (304)558-9591 | Perry.J.Keller@wv.gov | 195 | 0 | C | 65 |  | 65 |  | 65
30 | Wisconsin DOT | Erik Emerson | Erik Emerson | (608) 266-2842 | erik.emerson@dot.wi.gov | 325 | 65 | C | 65 | y | 65 |  | 65 |  | 65 |  | 65
| FFY Totals >>> |  |  |  | Totals 2023-2027 | Contracted | Balance |  | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027
| Total # of states committed | [7 empty] | 27 |  | 27 |  | 21 |  | 10 |  | 10
| Total # of states obligated | [7 empty] | 26 |  | 3 |  | 0 |  | 0 |  | 0
| Total # of states if filter active | [7 empty] | 27 |  | 27 |  | 21 |  | 10 |  | 10
| Total committed |  |  |  | 6027.5 |  |  |  | 1672.5 |  | 1722.5 |  | 1332.5 |  | 650 |  | 650
| Total obligated |  | * | 96.11% | 1802.5 | 814.736 | 987.764 |  | 1607.5 |  | 195 |  | 0 |  | 0 |  | 0
| Total arrears |  |  |  | 4225 |  |  |  | 65 |  | 1527.5 |  | 1332.5 |  | 650 |  | 650
| Totals if filter active |  |  |  | 6027.5 |  |  |  | 1672.5 |  | 1722.5 |  | 1332.5 |  | 650 |  | 650
|  |  | * | for 2023 only
Estimated spending plans
Regular program | [8 empty] | 2023 |  | 2024 |  | 2025 |  | 2026 |  | 2027
| Cummulative Commitments | [7 empty] | 1672.5 |  | 3395 |  | 4727.5 |  | 5377.5 |  | 6027.5
| Estimated Obligations | [7 empty] | 910 |  | 1820 |  | 1300 |  | 650 |  | 1347.5
| Cummulative Obligations | [7 empty] | 910 |  | 2730 |  | 4030 |  | 4680 |  | 6027.5
| Spending [invoicing] | [7 empty] | 100 |  | 1500 |  | 1500 |  | 1000 |  | 1927.5
| Cummulative spending | [7 empty] | 100 |  | 1600 |  | 3100 |  | 4100 |  | 6027.5
Supplementary projects
| Supp transfers and task orders | [7 empty] | 600 |  | 400 |  | 300 |  | 300 |  | 500
| Cummulative Supp transfers | [7 empty] | 600 |  | 1000 |  | 1300 |  | 1600 |  | 2100
| Supplementary spending | [7 empty] | 100 |  | 600 |  | 500 |  | 500 |  | 400
| Cummulative supp spending | [7 empty] | 100 |  | 700 |  | 1200 |  | 1700 |  | 2100
Est. regular + supp spending | [8 empty] | 200 |  | 2100 |  | 2000 |  | 1500 |  | 2327.5
Cummulative total spending | [8 empty] | 200 |  | 2300 |  | 4300 |  | 5800 |  | 8127.5
Current MASH 5-343 | [8 empty] | 400
Grand Total thru Dec 2023 | [8 empty] | 600
| Commitment Status |  |  |  | # of states |  |  | Tot potential commits 2023 | Cum tot of poss. + committed 2023
C | Tot. committed online |  |  |  | 27 |  |  |  | 1672.5
E | Tot. confirmed by email |  |  |  | 1 |  |  | 65 | 1737.5
U | Tot. undecided |  |  |  | 0 |  |  | 0 | 1737.5
R | Tot. unresponsive |  |  |  | 0 |  |  | 0 | 1737.5
N | Tot. declined |  |  |  | 2
Note on I3: Mohamedali, Mustafa: Per TM email and state respondents: C=Committed formally online E=committed by Email U=Undecided N=Not participating R=unResponsive
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: i = in process
Note on M4: Moeckel, Tim: 7/30/24: Mara sent e-mail notifying that Alabama obligated $65K funds for 2024. Alabama still has not posted its 2024 commitment on the TPF 5(501) website.
Note on K5: Mohamedali, Mustafa: Obligated May 17. 2023
Note on J7: Mohamedali, Mustafa:
Note on J8: Mohamedali, Mustafa: 5/18/23 - in addition CT has obligated $524,795 for supplemental project(s)
Note on I9: Mohamedali, Mustafa: Helped Nikki Johnson walk through and enter DellDOT commitment. She's awaiting director's approval for the 2024/25 commitments
Note on K9: Mohamedali, Mustafa: Obligated 6/15/23
Note on L9: Moeckel, Tim: 7/19/23: Per TPF 5(501) pooled fund website, Delaware posted its 2024 commitment.
Note on M9: Mohamedali, Mustafa: Per Mara's email Aug 31, 2023
Note on K10: Mohamedali, Mustafa: 230720 FL's transfer is being processed by FHWA
Note on I11: Moeckel, Tim: changed status, I see that Idaho posted their commitment
Note on I12: Mohamedali, Mustafa: See email 9/14 Megan Swanson 5/26/23: Commitments posted for all 5 years.
Note on K12: Mohamedali, Mustafa: 230719 FL's transfer is being processed by FHWA
Note on K15: Mohamedali, Mustafa: Obligated 6/15/23
Note on K18: Mohamedali, Mustafa: Obligated May 17, 2023
Note on I21: Mohamedali, Mustafa: Email Brad.julian@dot.nm.gov NM DOT Jan 17
Note on L26: Moeckel, Tim: 7/19/23: Looked at Pooled Fund webpage and PA has posted its commitment for 2024 and 2025.
Note on N26: Moeckel, Tim: 7/19/23: Looked at Pooled Fund webpage and PA has posted its commitment for 2024 and 2025.
Note on I28: Mohamedali, Mustafa: Per email 2/22/2023
Note on K28: Mohamedali, Mustafa: 230720 funds transferred to FHWA per Pawel Polaczyk email
Note on I33: Mohamedali, Mustafa: Per email 9/6/22 WisDOT uses non SPR funds and apparently does not want to make a commitment online Moeckel, Tim: Per latest correspondence (9/7/22 Diane Gurtner WisDOT), It appears WisDOT research office will post commitment online so I'm changing WI Ph.3 status to "E" until their commitmenent is posted. 9/8/22 - Evelyn B called and I have added WisDOT to the commitment page and they have posted for all 5 years!
Note on J57: Mohamedali, Mustafa: In addition, for 2023 Jul-Dec, I would recommend a provision of about $400k for TPF5-343. This would bring the 2023 total to $600k approx.

## 5-501 Project Priorities
TPF 5(501) Roadside Safety Pooled Fund - FFY2024 Research Projects (updated 10/16/23)
Year-Rank | Vote Count | Project ID | Project Name | Cost | Time | Lead/Tech Rep | Principal Investigator | Comment | Task Order
FFY2024 Prioritized/Funded Projects in Prioritized Order
2024-01 | 102 | 2024-06-LSRB | Short Radius Guardrail System (SRGS) - Additional Testing | 171000 |  | Tim Moeckel (WA) | Akram Abu-Odeh/ Sun Hee Park
2024-02 | 154 | 2024-07-LSRB | MASH TL-3 Design, Testing, and Evaluation of a Flared Guardrail System - Phase 2 | 174500 |  | Tim Moeckel (WA) | Sun Hee Park/ Nauman Sheikh
2024-03 | 208 | 2024-03-LSRB | Determine MASH TL-3 and/or TL-2 Compliance of MGS with Half-Post Spacing and Quarter-Post Spacing with no soil backup | 220000 | 15-Months | Nina Ertel (PA) | James Kovar
2024-04 | 220 | 2024-03-BD | Evaluation of Multi-Post Large Sign Supports with Slip Base and Slip Hinge | 213400 |  | Scott Jollo (OR) | Roger Bligh
2024-05 | 224 | 2024-01-BR | Bridge Rail End Treatments Guidance for Constrained Sites | 153900 |  | Mary McRae (AK), Sara Manning (AK), Ali Hangul (TN), Ted Whitmore (WV) | Akram Abu-Odeh
2024-06 | 225 | 2024-04-LSRB | Deflection Distances for MASH TL-2 (maybe TL-1) of MGS with Half-Post and Quarter-Post Spacing | 15000 | 6-Months | Nina Ertel (PA) | James Kovar
2024-07 | 244 | 2024-04-BD | MASH Evaluation of Square Tubing Slip Base Sign Support Systems | 117000 |  | Scott Jollo (OR) | Nathan Schultz
2024-08 | 245 | 2024-02-LSRB | Determine MASH TL-3 and/or TL-2 Compliance of MGS with Half-Post Spacing and Quarter-Post Spacing with Curb (6-Inch Max Height) | 216000 | 15-Months | Nina Ertel (PA) | James Kovar
2024-09
|  |  | Subtotal (Funded Projects) | 1280800
FFY 2024 Recurring Projects
2024 |  |  | 2024 Program Administration and Development | 83000 | 12-Months | Tim Moeckel (WA) | Nauman Sheikh
|  |  | 2024 Website and MASH Database Update Support | 16500 | 12-Months | Tim Moeckel (WA) | Nauman Sheikh
2024 |  |  | 2024 Engineering Support Services and Recommendations for Roadside Safety Issues for Member States (Professional Opinions) | 50000 | 12-Months | Jim Danila (MA) | Nauman Sheikh
2024 |  |  | 2024 Simulation Modeling Improvements and Updates (PROPOSED) | 60000 | 12-Months | Tim Moeckel (WA) | Akram Abu-Odeh
2024 |  |  | 2024 Annual Meeting Coordination and Travel | 112000 | ~ | Tim Moeckel (WA) | Roger Bligh | Estimated cost based off 2023 work order
2024 |  |  | Reserve (this can change slightly but keep around $50K) | 135400
|  |  | Subtotal (Recurring Projects, Reserve) | 456900
|  |  | Total (All Projects) | 1737700
|  |  | Total Estimated Budget (Participating State Funding) | 1737700 |  |  |  | updated 10/3/23: 27 States Posted Commitments = $1.723 million Funding FFY 2023 Balance Brought Forward = $15.2K Estimated Funds Total Estimated Funds = $1.738 million
|  |  | Difference Between All Project Total Costs & Total Estimated Budget | 0 |  |  |  | Should be zero to balance -- $XXXX uncommitted funds going into Reserve
|  |  | Total Obligated and Transferred Funds (as of X/XX/XXXX) | 0 |  |  |  | From TPF 5(501) Phase 3 spreadsheet
Remaining Unfunded FFY2024 Proposals in Prioritization Order
2024-21
2024-20
2024-23
2024-13
2024-10
2024-22
2024-12
2024-24
2024-26 | 246 | 2023-03-LSRB | Placement of Underground Obstructions by Guardrail Posts | 211800 |  | Erik Emerson (WI)
2024-14 | 247 | 2024-02-BD | Evaluation of Triangular Slip Base for Breakaway Luminaire Supports | 164700 |  | Scott Jollo (OR)
2024-15 | 250 | 2024-02-LCB | Foundation Criteria and Slope Design Guidance for Structurally Independent Concrete Barrier | 142000 |  | Khamsai Yang (MN)
2024-19 | 259 | 2024-08-LSRB | Development and Evaluation of a Thrie Beam Transition between 31" Median Guardrail and Median Single Slope Concrete Barrier | 105000 |  | Khamsai Yang (MN)
2024-11 | 272 | 2023-03-BR | Assessment of Bike Pedestrian Railings Attached to Crashworthy Barriers | 106300 |  | Patrick O'Neill (WA)
2024-17 | 276 | 2019-06-LCB | MASH TL-4 Testing and Evaluation of Free-Standing F-Shape Portable Concrete Barrier | 215000 | 12-Months | Chris Henson (OR), Andrew Pott (CO)
2024-16 | 293 | 2024-01-LCB | MASH TL-3 Compliance of Tall Precast F-Shape Concrete Median Barrier - Pinned to Asphalt | 326000 |  | Nina Ertel (PA)
2024-18 | 304 | 2024-01-WZ | White Paper on National Availability of MASH Approved Trailer Mounted Equipment (Category 4 Devices) | 27000 |  | Brian Crossley (PA)
2024-25 | 362 | 2024-01-LSRB | MASH TL-3 Compliant Thrie-Beam Guardrail System for Vehicle and Pedestrian Safety - Phase 1 | 189700 |  | Ali Hangul (TN)
|  |  | Value of unfunded proposals | 1487500
|  |  | Value of funded & unfunded proposals (not incl. cont. projects) | 2768300
|  |  | Value of all projects (funded/unfunded proposals & cont. projects) | 3225200

## TAC Contact Info
TPF 5(501) Roadside Safety Pooled Fund - Phase 3
TAC Members Roster - Leads and Seconds/FHWA/TTI
Updated: 9/26/2023 (tjm)
State | Name | Lead | Second | Title | Division | Agency | Phone | Cell | Email
AK | Mary F McRae | √ |  | Design and Construction Standards Engineer | Design and Engineering Standards | Alaska Department of Transportation and Public Facilities | (907) 465-1222 |  | mary.mcrae@alaska.gov
AK | Michael Hills |  | √ |  |  | Alaska Department of Transportation and Public Facilities |  |  | michael.hills@alaska.gov
AL | Wade Henry, P.E. | √ |  | Assistant State Design Engineer | Design Bureau, Final Design Division | Alabama Dept. of Transportation | (334)242-6464 | (334) 657-6736 | henryw@dot.state.al.us
AL | Stanley (Stan) C. Biddick, P.E. |  | √ | State Design Engineer | Design Bureau | Alabama Dept. of Transportation | (334)242-6488 | (334) 850-0007 | biddicks@dot.state.al.us
CA | Bob Meline, P.E. | √ |  |  | Office of Materials and Infrastructure Division of Research and Innovation | Caltrans | (916) 227-7031 |  | Bob.Meline@dot.ca.gov
CA | John Jewell, P.E. |  | √ | Senior Crash Testing Engineer | Office of Safety Innovation and Cooperative Research Division of Research, Innovation & System Information |  | (916) 227-5824 |  | John_Jewell@dot.ca.gov
CO | Andy Pott, P.E. | √ |  | Senior Bridge Design and Construction Engineer | Division of Project Support, Staff Bridge Design and Construction Management | Colorado Dept. of Transportation (CDOT) | 303-512-4020 | 720-454-4045 | andrew.pott@state.co.us
CO | Shawn Yu, P.E. |  | √ | Miscellaneous (M) Standards and Specifications Unit Manager | Division of Project Support, Construction Engineering Services (CES) | Colorado Dept. of Transportation (CDOT) | 303-757-9474 | 720-635-7817 | shawn.yu@state.co.us
CO | David Kosmiski, P.E. |  | √ | Miscellaneous (M) Standards Engineer | Division of Project Support, Construction Engineering Services (CES) | Colorado Dept. of Transportation (CDOT) | 303-757-9021 | 720-883-6170 | david.kosmiski@state.co.us
CO | Amin Fakhimalizad |  | √ | Assistant Miscellaneous (M) Standards Engineer | Division of Project Support, Construction Engineering Services (CES) | Colorado Dept. of Transportation (CDOT) | 303-757-9229 |  | amin.fakhimalizad@state.co.us
CO | Man (Steve) Yip |  | √ |  | Division of Project Support, Construction Engineering Services (CES) | Colorado Dept. of Transportation (CDOT) |  |  | man.yip@state.co.us
CT | David Kilpatrick | √ |  | Transportation Supervising Engineer | Division of Facilities and Transit - Engineering Services | Connecticut Dept. of Transportation | (860) 594-3288 |  | David.Kilpatrick@ct.gov
DE | Craig Blowers | √ |  | Construction Resource Engineer | Construction Section | Delaware DOT | (302)760-2336 | (302)236-9816 | Craig.Blowers@delaware.gov
DE | James Osborne |  | √ | Traffic Safety Programs Manager | Traffic Operations | Delaware DOT | (302)659-4651 | (302)542-7201 | James.Osborne@delaware.gov
FHWA HQ | Eduardo Arispe | √ |  | Research Highway Safety Specialist | Federal Highway Administration Turner-Fairbank highway Research Center | U.S. Department of Transportation | (202) 493-3291 |  | Eduardo.Arispe@dot.gov
FHWA HQ | Dick Albin |  | √ | Senior Safety Engineer | Office of Innovation Implementation, Safety & Design Team | U.S. Department of Transportation |  | (303) 550-8804 | Dick.Albin@dot.gov
FHWA HQ | Matt Hinshaw, M.S., P.E. |  | √ | Highway Safety Engineer | FHWA Office of Safety | U.S. Department of Transportation | 360-619-7677 |  | matthew.hinshaw@dot.gov
FHWA FLH | Christine Black | √ |  | Highway Safety Engineer | Central Federal Lands Highway Division |  | (720) 963-3662 |  | Christine.black@dot.gov
FHWA FLH | Isbel Ramos-Reyes |  | √ | Lead Safety and Transportation Operations Engineer | Eastern Federal Lands Highway Division |  | 703-948-1442 |  | isbel.ramos-reyes@dot.gov
FL | Richard Stepp | √ |  |  |  | Florida Department of Transportation |  |  | Richard.Stepp@dot.state.fl.us
FL | Derwood C. Sheppard, Jr., P.E. |  | √ | Standard Plans Publication Eng. | FDOT Roadway Design Office | Florida Department of Transportation | (850) 414-4334 |  | Derwood.Sheppard@dot.state.fl.us
IA | Daniel Harness | √ |  |  | Office of Design – Methods | Iowa Department of Transportation |  |  | Daniel.Harness@iowadot.us
IA | Chris Poole |  | √ | State Traffic Engineer | Traffic and Safety Bureau | Iowa Department of Transportation |  |  | Chris.Poole@iowadot.us
ID | Marc Danley | √ | [6 empty] | Marc.Danley@itd.idaho.gov
ID | Kevin Sablan |  | √ | Design/Traffic Engineer |  | Idaho Transportation Department | (208) 334-8558 |  | Kevin.sablan@itd.idaho.gov
IL | Martha A. Brown, P.E. | √ |  | Safety Policy & Initiatives Engineer | Bureau of Safety Programs and Engineering | Illinois Department of Transportation | (217) 785-3034 |  | Martha.A.Brown@illinois.gov
IL | Edgar Galofre |  | √ | Safety Design Engineer | Bureau of Safety Programs and Engineering | Illinois Department of Transportation | (217) 558-9089 |  | Edgar.Galofre@Illinois.gov
LA | Chris Guidry | √ |  | Bridge Manager | Bridge & Structural Design Section | Louisiana Department of Transportation & Development | (225) 379-1328 |  | Chris.Guidry@la.gov
LA | Carl Gaudry |  | √ | Bridge Design Manager | Bridge & Structural Design Section | Louisiana Department of Transportation & Development |  |  | Carl.Gaudry@la.gov
MA | James Danila | √ |  | Assistant State Traffic Engineer |  | Massachusetts Department of Transportation | (857) 368-9640 |  | James.Danila@state.ma.us
MA | Alex Bardow |  | √ | Director of Bridges and Structure |  | Massachusetts Department of Transportation | (857) 368-9430 |  | Alexander.Bardow@state.ma.us
MD | Philip Brentlinger | √ |  |  |  | Maryland State Highway Administration |  |  | pbrentlinger@mdot.maryland.gov
MI | Carlos Torres, P.E. | √ |  | Crash Barrier Engineer | Geometric Design Unit, Design Division | Michigan Department of Transportation | (517) 335-2852 |  | torresc@michigan.gov
MN | Khamsai Yang | √ |  | Design Standards Engineer | Office of Project Management and Technical Support | Minnesota Department of Transportation | (651) 366-4622 | 612-322-5601 | Khamsai.Yang@state.mn.us
MN | Brian Tang |  | √ | Assistant Design Standards Engineer | Office of Project Management and Technical Support | Minnesota Department of Transportation | (651) 366-4684 |  | brian.tang@state.mn.us
MO | Amy Crawford | √ |  |  |  | Missouri Department of Transportation |  |  | Amy.Crawford@modot.mo.gov
MO | Kaitlyn (Katy) Bower |  | √ | Roadside Design Specialist |  | Missouri Department of Transportation | 573-472-9028 |  | kaitlyn.bower@modot.mo.gov
NM | Brad Julian | √ |  | Traffic Technical Support Engineer |  | New Mexico DOT | 505 827-3263 | 505-469-1405 | Brad.Julian@dot.nm.gov
OH | Don Fisher, P.E. | √ |  |  |  | Ohio DOT | (614) 387-2614 |  | don.fisher@dot.ohio.gov
ON | Kenneth Shannon, P. Eng. | √ |  | Senior Engineer, Highway Design (A) |  | Ontario Ministry of Transportation | (905) 704-3106 |  | Kenneth.Shannon@ontario.ca
OR | Christopher Henson | √ |  | Senior Roadside Design Engineer | Technical Services Branch | Oregon Department of Transportation | (503) 986-3561 |  | Christopher.S.Henson@odot.state.or.us
PA | James Borino, Jr. | √ |  | Chief, Standards and Criteria Unit | Highway Design and Technology Division | Pennsylvania DOT | (717)612-4791 |  | jborino@pa.gov
PA | Evan Pursel |  | √ | Senior Civil Engineer | Highway Design and Technology Division | Pennsylvania DOT | (717) 705-8535 |  | epursel@pa.gov
PA | Nina Ertel |  | √ | Project Development Engineer | Highway Design and Technology Division | Pennsylvania DOT | (717) 425-7679 |  | nertel@pa.gov
TN | Ali Hangul | √ |  | Asst. Director, Design Standards and Policy | HQ Roadway Design and Office of Aerial Surveys | Tennesee DOT | (615) 741-0840 |  | Ali.Hangul@tn.gov
TTI | Roger Bligh | √ |  | Senior Research Engineer | Roadside Safety and Physical Security | Texas A&M Transportation Institute | (979) 317 2703 |  | r-bligh@tti.tamu.edu
TTI | Nauman Sheikh | √ |  | Research Scientist | Roadside Safety and Physical Security | Texas A&M Transportation Institute |  |  | n-sheikh@tti.tamu.edu
TTI | Ariel Sheil |  | √ | Research Assistant | Roadside Safety and Physical Security | Texas A&M Transportation Institute |  | (979) 595-3350 | A-Sheil@tti.tamu.edu
TTI | Lance Bullard | √ |  | Senior Research Engineer | Roadside Safety and Physical Security | Texas A&M Transportation Institute | (979) 317-2855 |  | l-bullard@tti.tamu.edu
TX | Chris Lindsey | √ |  |  | Design Division | Texas Department of Transportation | (512) 416-2750 |  | Christopher.Lindsey@txdot.gov
TX | Taya Retterer |  | √ | TxDOT Bridge Standards Engineer | Bridge Division | Texas Department of Transportation | (512) 416-2719 |  | Taya.Retterer@txdot.gov
UT | Shawn Debenham | √ |  | Roadside Safety Manager | Traffic and Safety Division | Utah Department of Transportation | (801) 971-9575 |  | sdebenham@utah.gov
WA | Tim Moeckel | √ |  | Roadside Safety Engineer | Development Division | Washington State Dept. of Transportation | (360) 704-6377 | (360) 972-8050 | moecket@wsdot.wa.gov
WA | Kevin Burch |  | √ | Policy Support Engineer | Development Division | Washington State Dept. of Transportation |  |  | burchk@wsdot.wa.gov
WA | Mustafa Mohamedali |  | √ | Research Manager/Engineering | Trans Safety & System Analysis Research & Library Services | Washington State Dept. of Transportation | (360) 704-6307 | (360) 556-3332 | Mohamem@wsdot.wa.gov
WI | Erik Emerson P.E. | √ |  | Standards Development Engineer Roadside Design | Bureau of Project Development | Wisconsin Department of Transportation | (608) 266-2842 |  | Erik.Emerson@wi.gov
WV | Donna Hardy | √ |  | Mobility, ITS & Safety Engineer |  | WV Department of Transportation | 304-414-7338 |  | Donna.J.hardy@wv.gov
WV | Ted Whitmore | √ |  | Traffic Services Engineer | Traffic Engineering | WV Division of Highways | (304)414-7373 |  | Ted.J.Whitmore@wv.gov
Alaska, Alabama, California, Colorado, Connecticut, Delaware, Florida, Iowa, Idaho, Illinois, Louisiana, Massachusetts, Maryland, Michigan, Minnesota, Missouri, New Mexico, Ohio, Ontario, Oregon, Pennsylvania, Tennessee, Texas, Utah, Washington, Wisconsin, West Virginia State Count = 27